## WPYear2 VFDM
Second year workplan- Volta project Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali and Togo
Project No:
Project Name: | Integrating Flood and Drought Management and Early Warning for Climate Change Adaptation in the Volta Basin
Implementing Agency: | WMO
Executing Agency: | WMO/GWP-WA/VBA
Source of funding : | Adaptation Fund
Output | Expected Output Description | Activities under Output | Expected Deliverables | Main coordinator | WMO | VBA | GWP-WA | International and National Partners to be involved | 2020-2021
[9 empty] | Quarter 3 | Quarter 4 | Quarter 1 | Quarter 2 | Quarter 3
Component 1: Develop capacity and established frameworks at the local, national and regional levels to ensure risk informed decision-making
Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms
Output 1.1.1 | Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | 1.1.1.3 Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | Workshop reports Presentation and Communication supports National mission reports | GWP-WA |  |  |  | NMSs, NHSs, Geographic institute, Other relevant, Aghrymet, WASCAL | X | X
|  | 1.1.1.4 Conduct pilot field studies (focus group discussion and semi-structured interviews) with communities to identify the multi-dimensional drivers of vulnerability and risk (social, economic, ecological, cultural, political and infrastructural determinants of vulnerability) in the Volta Basin areas highly exposed to different hydrometeorological hazards | Methodology note / Guidelines Mission report | WMO | WMO with CERFE will do the pilot visits ( sites) with local consultants, VBA and GWP-WA WMO will follow-up wth Ghana consultant | VBA will participate in the pilot testing of 3 sites and later follow-up with local consultant of Mali, CI and Burkina Faso | GWP-WA will participate in the pilot testing of 3 sites and later follow-up with local consultant of Mali, CI and Burkina Faso | NMSs, NHSs CIMA, IUCN, CERFE, Other relevant |  | X | X
|  | 1.1.1.5 Draft the field studies reports and the Volta-atlas | Missions reports, Volta-Atlas | WMO | WMO with CERFE and CIMA will integrate the information from the local consultants and visulaize in the VOLTALARM Platform |  |  | VBA, GWP-WA, NMSs, NHSs CIMA, Other relevant | X | X | X
Output 1.1.2 | Database of VCERs, floods and drought related risk maps are developed | 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise at the VBA observatory, the NMHSs services and other relevant services (e.g. Geographical Institute, Civil security, etc.). Purchase additional equipment if necessary | Methodology note Database Mission report | WMO | Partially done under the National Consultation mission |  |  | NMSs, NHSs CIMA, Geographic institute, Other relevant | X | X | X
|  | 1.1.2.2 Create the Volta Basin information exchange IT network by connecting the VBA observatory and the national services | Assessment and Reporting | VBA |  |  |  | OMM, GWP-WA, NMSs, NHSs CIMA, Geographic institute, Other relevant | X | X | X
|  | A) Concept note and tool to be developed |  | WMO | WMO prepared the concept note | VBA to review the concept note and share with National FPs and prepare the list of IT and Database manager to be interviewed | GWP-WA to review the concept note and share with National FPs and prepare the list of IT and Database manager to be interviewed | check concept note | X | X | X
|  | B) Data and Information collection through National focal points |  | VBA | WMO/CIMA will validate and integrate necessary information in the VOLTALARM | VBA will coordinate with the National focal points in the collection of the data and information and provide collected information to the WMO/CIMA | GWP-WA will support VBA in the data and information collection
|  | C.1) Country assessment mission by WMO IT expert |  | WMO | WMO and CIMA will provide remote technical support in dveeloping the methodology and tools for the data collection | VBA IT expert will test the tool initially in one countriy and incorporate lesson learnt and experience in the tool. Once the tool is finalized, conduct similar assessment in other 5 countries. | GWP-WA PMT will provide remote support in the preparation and conducting mission |  | X | X | X
|  | C.2) Organization of the mission in other four countries and applying the tool and methodology |  | VBA | WMO will review the information collected by the VBA IT experts in the four country. | VBA IT expert will implement similar methodolgy applied in Burkina Faso and Ghana in other four countries | GWP-WA PMT will provide remote support in the preparation and conducting mission
|  | D) Architecture of the network connection is developed(where it will be present, access to whom etc.) for each country including How database at the national level (as well local level) can be connected to the regional level (physically or using cloud ) and Number and Type of equipments to be purchased for developing database at national and regional level |  | WMO | WMO, CIMA and VBA to prepare architecture of the n/w connection of BF and Ghana | VBA will prepare report for other 4 countries | GWP-WA to support VBA in the development of the report |  |  | X | X
|  | 1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | list and characteristics of equipments Calls for tenders Equipment installation report | WMO |  |  |  |  | X | X | X | X
|  | Procurement of the equipments and delivery in the countries |  | WMO | WMO will do the procurement of the equipments and materials as per the National report prepared under 1.1.2.2 | VBA will be collaborate with the National Agencies to install the equipments at the NMHSs | GWP-WA will be collaborate with the National Agencies to install the equipments at the NMHSs |  |  | X | X | X | X
|  | MCH database to be installed and running (connecting with the exisitng database and information) |  | WMO | WMO MCH Expert will install the MCH Database in the country and migrate existing information to the MCH | VBA will provide necessary support in the installation and operation of the MCH Database | GWP-WA will provide necessary support in the installation and operation of the MCH Database |  |  | X | X | X | X
|  | Training to the Hydro-Met and IT/DB experts of each country |  | WMO | WMO MCH expert will prepare concept note and provide training to the Staffs working in NMHSs and other relevant authorities NMHSs of each country will organize the training at their premises. WMO will attend training in Ghana and BF | VBA will participate in the training held in Mali, CI and BF | GWP-WA will participate in the training held in Benin, Togo and BF |  |  | X | X | X | X
|  | Data related to VCERs, Hydro-met are added from the six countries ( mainly for the region under Volta Basin and from existing projects ) to the MCH database |  | WMO | Follow-up with countries to provide data and information for the risk maps and EWS | Follow-up with countries to provide data and information for the risk maps and EWS | Follow-up with countries to provide data and information for the risk maps and EWS |  |  | X | X | X | X
|  | 1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | Concept note Workshop report, Maps, communication supports Mission report | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant | X | X | X | V
|  | Connect or link already existing risk maps available at the national level (through diferent projects) for the Volta Basin region |  | WMO | WMO will coordinate with various partners from past and on-going projects as well as to integrate the project and Globally available information in the myDewetra platform | VBA to provide support in coordination with the National project partners and projects (FDMT with DHI-UNEP) | GWP-WA to provide support in coordination with the National project partners | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant | X | X | X
|  | Concept note development, methodolgy and sharing with the National Focal points |  | WMO | WMO to prepare the concept note and methodology | support in the development of the concept note | support in the development of the concept note | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant |  | X
|  | Planning and Preparation of the Risk map development training |  | GWP-WA | WMO prepare to train National Staffs for the development of Vulnerability and risk maps -methodology and tool development | Identification of National staffs with GIS skills and knowledge Availability of background information on risk maps from the National agencies or project partners | Identification of National staffs with GIS skills and knowledge Availability of background information on risk maps from the National agencies or project partners | NMSs, NHSs Geographic institute, Other relevant |  | X
|  | Training (2.5 days in each country) are provided to develop flood and drought risk maps for each country staffs Ghana-12 technical staffs BF-12 technical staffs Benin and Togo-8 technical staffs CI and Mali-8 technical staffs |  | GWP-WA | WMO will facilitate the National Training Workshop to present the methodology, tools for developing vulnerability and exposure maps. | organization of the National workshop and participation to the Ntaional workshop IN CI, Mali and BF | organization of the workshop and Participation to the National workshop in Togo, Benin and BF | NMSs, NHSs Geographic institute, Other relevant |  |  | X | X | X
|  | Trained participant provide more inputs to the areas for which the data is not completely available and also run Models or develop risk maps for that region |  | GWP-WA and NFP participants | The project partners ensure trained participants continue to provide support and participation on the tasks requested o carry out in relation to the development of floods and drought risk maps |  |  | NMSs, NHSs Geographic institute, Other relevant |  |  | X | X | X
|  | 1.1.2.5 Assign roles and responsibilities to the agencies and organisations to regularly complement and improve the database and risk maps |  | WMO/VBA |  |  |  | NMSs, NHSs Geographic institute, Other relevant |  | X | X
|  | Lists of National level focal points and assigning roles and responsibilities |  | WMO/VBA | Identify the FPs who will contribute in updating the risk maps with new information and data during the course of the project as well as after the completion of the project |  |  | NMSs, NHSs Geographic institute, Other relevant |  | X | X
Output 1.1.3 | Capacity of stakeholders to use Floods and Drought risk maps is enhanced | 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps |  | WMO |  |  |  | NMSs, NHSs CIMA, Geographic institute, Other relevant |  | X | X | X
|  | Integrate information from the National trained staffs (preparing the shape maps on vulnerability and exposure) and provide remote assistance in the development of the risk maps |  | WMO | WMO to prepare the flood and drought Hazard model maps for the entire Volta Basin for the floods and drought events WMO to review the work done by the National participants and provide assitance in developing the vulnerabilities and exposure maps. PMT to provide support in collecting information from the National participants as well as from the National Agencies | PMT to provide support in collecting information from the National participants as well as from the National Agencies | PMT to provide support in collecting information from the National participants as well as from the National Agencies | NMSs, NHSs CIMA, Geographic institute, Other relevant |  | X | X | X
|  | 6 National workshop with same staffs to follow the work done after training under 1.1.2.4 (after 30-45 days) | Follow-up to 1.1.2.4 | GWP-WA- | WMO Facilitate the National Training Workshop (2.5 days in each country) | organization of the National workshop and participation to the Ntaional workshop IN CI, Mali and BF | organization of the workshop and Participation to the National workshop in Togo, Benin and BF | NMSs, NHSs Geographic institute, Other relevant |  |  | X | X
|  | Trained participant provide more inputs to the areas for which the data is not completely available and also run Models or develop risk maps for that region |  | GWP-WA NFP | The project partners ensure trained participants continue to provide support and participation on the tasks requested to carry out in relation to the development of floods and drought risk maps |  |  | NMSs, NHSs Geographic institute, Other relevant |  |  | X | X
|  | WMO together will external consultants will integrate the vulnerability, hazards, exposure maps in the VOLTALARM EWS |  | WMO | WMO will merge the shape maps or layers of vulnerability, exposure, hazards to develop the risk maps and visualize in the VOLTALARM platform | PMT to provide necessary support to the External Partners and follow-up with the National Focal points to gather missing information |  |  |  |  | X | X
|  | 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement | Concept note, Workshop report, presentation and communication supports | GWP-WA |  |  |  | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant |  | X | X | X | X
|  | Regional workshop with staffs and communities individuals to follow the work done after training under 1.1.3.1 (after 30-45 days) | Follow-up to 1.1.2.4 and 1.1.3.1 | GWP-WA | PMT to develop the concept note and facilitate the regional Training Workshop (2.5 days in each country) | organization of the regional workshop | organization of the regional workshop | NMSs, NHSs Geographic institute, Other relevant |  |  |  | X | x
|  | 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries |  | GWP-WA |  |  |  | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant |  |  |  | X | X
|  | Design and development of the risk maps (techncial contents) on the banner, maps to overcome for the National agencies offices and important risk areas in the Volta Basin |  | WMO | Develop together the content . Also share with National Agencies and community on risks |  |  | NMSs, NHSs Geographic institute, community representative |  |  |  | X | x
|  | Printing of the materials and delivering it to the National agencies and communities at risks |  | GWP-WA |  |  | printing and delivering to National agencies and communities at risk | NMSs, NHSs Geographic institute, community representative
Output 1.1.4 | Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps for the stakeholders and Adaptation Fund project technical committee | Terms of reference, Technical report | WMO |  |  |  | GWP-WA, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant |  |  |  |  | X
|  | Development of the risk maps guideline document to make better understand the risk areas and measures to take in case of floods and drought events |  | WMO | WMO to prepare the first draft | VBA to contribute and share it with National focal points for review | VBA to contribute and share it with National focal points for review | NMSs, NHSs Geographic institute, community representative |  |  |  | X | x
|  | 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) | Communication support Pedagogical materials elaborated | GWP-WA | Prepare awareness document or videos based on the information available from 1.1.3.3, 1.1.4.1 |  |  | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant |  |  |  |  | X
Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment,etc.) into current practices and knowledge
Output 1.2.1 | Scenarios for socio-economic and environment development along with the climate change projections are collected | 1.2.1.1 Gather all available information on climate change scenarios from best scientific studies and global databases for the Volta basin and select the most relevant datasets | Concept Note Database Mission report | WMO | WMO will develop the methodology and concept note and share it with the National stakeholders for the review Once methodology is accepted, WMO will prepare the climate scenarios for the current climate and as well as future climate impacts to various sector (socio-economics, environmental, water resources, agriculture etc.) | VBA and GWP will help in gathering the data and information (past and future climate projectons, urban, water resour ces, agriculture etc.) at the National level through one or two appointed Members of the National working Group |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
|  | 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades |  | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
|  | 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 |  | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
Output 1.2.2 | Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs using the future socio-economic and climate scenarios to determine changes in VCERs and risk maps | Concept Note Database Mission report | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
|  | 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes |  | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
|  | 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios |  | WMO |  |  |  | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant | X | X | X | X | X
Output 1.2.3 | Impact on environmental indicators is evaluated for current and future scenarios | 1.2.3.1 Define indicators related to environment conditions | Concept Note, methodology note Database, Methodologies and tools used for studying the impacts of environmental flow Mission report Mapping and geographical coordinates of selected (physical) thresholds | WMO | On-going from the first year |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.2 Collect and process information for various environmental indicators |  | WMO |  |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.3 Select thresholds and carry out analysis for current and future climate scenarios |  | WMO |  |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.4 Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology |  | WMO |  |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.5Draft report with the methodologies and tools used for studying the impacts of environmental flow |  | WMO |  |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.6 Drafting an integrated basin-wide wetland policy to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders. |  | WMO |  |  |  | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X
|  | 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity | ToR of workshop, presentation and communication supports, Workshop report, Mission report Number of roadmaps for implementing workshop guidelines in each of the 6 countries | VBA |  |  |  | IUCN, OMM, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs | X | X
Outcome 1.3: Risk management strategies in short, medium and long-term to be integrated into development plans (economic, social, environmental aspects)
Output 1.3.1 | Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps development and future impacts on VCERs assessment with examples of implementation on high vulnerable urbans and agricultural areas | TdR consultant Guidelines | WMO | WMO will prepare the guidelines document and share with the National stakeholders for review and suggestions | VBA will contribute with the necessary information from the regional and National level and sharing it with the National stakeholders | GWP-WA will provide necessary contribution in the development of the guidelines | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  |  |  |  | X
|  | 1.3.1.2 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) | Communication supports Pedagogical materials elaborated | GWP-WA | WMO will provide support to GWP-WA ind evelopment of the brochure or leaflets based on the guidleines document | VBA will provide support to GWP-WA in development of the brochure or leaflets based on the guidleines document | GWP-WA will finalize the brochure/leaflet and print it for distribution | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  |  |  |  | X
Output 1.3.2 | Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 1.3.2.1 Organize trainings and workshops with stakeholders (representatives of communities, local policy-makers and decision makers) to disseminate the information on future climate and risk changes and to obtain additional qualitative input | Concept Note Workshop reports roadmaps for implementing workshop guidelines in each of the 6 countries | GWP-WA | WMO will prepare concept note and necessary materials for the organization of the workshop and also provide support to the PMT for the facilitation of the workshops in the respective countries | VBA will provide necessary support in finalization fo the concept note and the organization of the workshop in each of the six countries. | GWP-WA will provide support in the organization of the wrorkshops | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  |  |  |  | X
|  | 1.3.2.2 a) Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments | training curriculum and guidelines | WMO (as this is next step of risk map development) | WMO will provide the training curriculum to conduct assessments and update risk maps |  |  | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  |  |  |  | X
|  | 1.3.2.2b) provide review to the training curriculum prepared in the abovesub-ctivities through the National agencies incharge | training curriculum and guidelines | VBA |  | VBA will provide necessary support in the review of the curriculum through the National working group and also follow-ups with the National participants involved in the development of the risk maps. | GWP-WA will provide necessary support in development of the curriculum and also follow-ups with the National participants involved in the development of the risk maps.
|  | 1.3.2.3 a) Design and develop action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders | ToR consultant, Mission report including the action plan for risk management | WMO (as this is next step of risk map development) | WMO will prepare the draft risk management action plan and strategies and share it with the National and regional patners for review. The draft risk management strategies and plan will be presented under activity 1.3.2.1. After the workshop, it will be finalized based on the comments received |  |  | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  |  |  |  | X
|  | 1.3.2.3 a) review the action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders |  | VBA |  | VBA will provide necessary support in the review of the draft action plan through National working groups and ensure finalization of the action plan with information from the National stakeholders | GWP-WA will provide necessary support in the development of the draft action plan and ensure finalization of the action plan with information from the National stakeholders
Component 2: Develop concrete adaptation and environmentally friendly actions with an integrated approach
Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities
Output 2.1.1 | Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 2.1.1.1 Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) | Concept Note, Methodology Note, List of participants, Manual of training (curriculum), ToR of workshop, communication and presentation supports, Workshop Report | GWP-WA/WMO | WMO will prepare the concept note and share with other partners (GWP-WA, VBA, UNITAR) for review and suggestions | VBA will prepare the list of the participants (atlast 5-8) from each country agencies together with WMO and VBA focal points | GWP-WA will provide support in development of the concept note and identifying participants at the National level | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant |  |  | X | X
|  | 2.1.1.2 Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas |  | WMO | Development of the E-learning courses using WMO moodle (for example) WMO will resue the existing training course and materials available from the previous trainings to the NMHS (Hydrometrists, forecasterst etc.) under the framework of E2E-EWS-FF components https://www.floodmanagement.info/floodmanagement/get-help/end-to-end-early-warning-systems-for-flood-forecasting-e2e-ews-ff/ Ensure the existing english modules of the courses are translated to French and instructors are provided for the modules of the courses Development of the new modules in collaboration of GWP-WA and UNITAR | VBA will provide support in identfying existing materials and new needs of training courses for the National staffs |  | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant |  | X | X | X | X
|  |  |  | GWP-WA | Concept note will be shared before 30 November 2020 and joint call to be organized at the first week of December 2020 |  | GWP will lead the development of various modules of the E-learning course together with WMO and UNITAR. Also, provide support in translating the new modules from English to French. Also, provide instructor for the new modules during the e-learning sessions
|  | 2.1.1.3 Organize the face-to-face training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises |  | GWP-WA | WMO and UNITAR will prepare practical exercises pertaining to the complete chain of the E2E-EWS-FF UNITAR will help in faciltating the regional workshop together with GWP-WA WMO and UNITAR preparationa and travel cost to Ouagadougou | VBA PMT will participate the regional workshop and will provide necessary support to GWP-WA in organizing the regional workshop | GWP-WA will organize the regional workshop ( 3 to 4 days for 36 participants in Ouagadougou, Burkina Faso) in close consultation with WMO(UNITAR) with the participants who have completed the e-learning courses and are certified. After the regional workshop, ensure new participants at the national level go through the e-learning courses and trained participants become mentor of them. GWP-WA staff will participate to the regional workshop so that they learn the practical exercises and can implement similar workshop in future. | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant |  |  | X | X | X
Output 2.1.2 | The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | Concept Note, mission report, List and characteristics of equipments | WMO | WMO in support of VBA and GWP-WA will assess the needs and capabilities of the Ntaional Agencies for using the VOLTALARM System Concept note will be developed and shared | VBA will provide necessary support in contacting various agencies at the National level | VBA will provide necessary support in contacting various agencies at the National level | VBA, GWP-WA, Other relevant |  | X | X | X | X
|  | 2.1.2.2 Buy, install and test the equipment needed to create VoltAlarm EWS | Calls of tender, Equipments | WMO |  |  |  | WMO, GWP-WA, Other relevant |  | X | X | X | X
|  | 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Webbased EWS | Concept note, Workshop report, presentation and communication supports | WMO | WMO will provide relevant trainings to the staffs of the National Agencies and as well as VBA experts to use the VOLTALARM system | VBA will provide support in the designing and conducting the training workshop | GWP-WA will help in providing support in the development of the training workshop. | VBA, GWP-WA, Other relevant |  |  | X | X | X
|  | 2.1.2.4 Write the operational manual including procedures and responsibilities | Manual including procedures and responsibilities | WMO | WMO will prepare the operational manual/implemntation plan including procedures and responsibilities in joint consultation with National and regional stakeholders | VBA will provide support in developing and reviewing the manual and providing support in disseminating the manual to the National Stakeholders. | GWP-WA will provide support in collecting feedback and suggestions from the National stakeholders. | VBA, GWP-WA, Other relevant |  |  | X | X | X
|  | 2.1.2.5 Run and maintain the VoltAlarm system | Calls of tender, Equipments | WMO | VOLTALARM, a cloud-based system is already designed and available for the users.Currently, it is maintained by WMO and at the end of 3rd year, National staffs and VBA will be trained for using the VOLTALARM system. Integration of existing information on risk maps and EWS needs to be carried out with countries and other project partners in the second and thrid year of the project | VBA will provide support in getting the necessary information from other completed projects (FDMT, FANFAR and other identified projects in the National Consultation report.) At the end of third year, VBA staff will be trained along with the National participants. | GWP-WA will provide necessary support in collecting existing project information (as described in the National consultation reports) from the Countries, which will be integrated in the VOLTALARM system | WMO, NMHs, NHSs, CIMA, other relevant, DHI |  | X | X | X | X
Output 2.1.3 | The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) | Concept Note, Mission report | WMO |  |  |  | VBA and other relevant organization |  | X | X | X | X
|  | 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data |  | WMO |  |  |  | VBA and other relevant organization |  | X | X |  | X
|  | 2.1.3.3 Develop the database of hydro-meteorological parameters, or interconnect with existing platforms | Database updated | WMO |  |  |  | VBA and other relevant organization |  | X | X |  | X
|  | 2.1.3.4 Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards | Concept note, Workshop report, presentation and communication supports | WMO |  |  |  | VBA and other relevant organization |  | X | X |  | X
Output 2.1.4 | Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | 2.1.4.1 Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas | Concept Note Database updated Mission reports | VBA |  |  |  | WMO and other relevant organization |  |  | X |  | X
|  | 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives |  | VBA |  |  |  | WMO and other relevant organization |  |  | X |  | X
|  | 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events |  | VBA |  |  |  | WMO and other relevant organization |  |  | X |  | X
|  | 2.1.4.4 Link the environment threshold with the threshold of flood and drought |  | VBA |  |  |  | WMO and other relevant organization |  |  | X |  | X
Output 2.1.5 | The procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | 2.1.5.1 For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) | Concept Note software to collect the meteorological and hydrological forecasts Procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily Mission reports | WMO |  |  |  | VBA, NMHs, NHSs, other relevant |  |  | X |  | X
|  | 2.1.5.2 For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events |  | WMO |  |  |  | VBA, NMHs, NHSs, other relevant |  |  | X |  | X
|  | 2.1.5.3 Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas |  | WMO |  |  |  | VBA, NMHs, NHSs, other relevant |  |  | X |  | X
|  | 2.1.5.4 Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory |  | WMO |  |  |  | VBA, NMHs, NHSs, other relevant |  |  | X |  | X
Output 2.1.6 | The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 10 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) | Concept Note Presentation supports Workshop reports | VBA | This will be done around December 2021. Preparation can start in June 2021 | This will be done around December 2021. Preparation can start in June 2021 | This will be done around December 2021. Preparation can start in June 2021 | WMO, GWP-WA, NMHs, NHSs, other relevant |  |  |  |  | X
|  | 2.1.6.2 Develop and test the web-based dissemination interface |  | WMO | This will be done around October-December 2021. Preparation can start in June 2021 | This will be done around October-December 2021. Preparation can start in June 2021 | This will be done around October-December 2021. Preparation can start in June 2021 | WMO, GWP-WA, NMHs, NHSs, other relevant |  |  |  |  | X
Output 2.1.7 | Knowledge and awareness about VoltAlarm are increased within the user groups | 2.1.7.1 Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS | Concept Note Presentation supports | VBA | This will be done around October-December 2021. Preparation can start in June 2021 | This will be done around October-December 2021. Preparation can start in June 2021 | This will be done around October-December 2021. Preparation can start in June 2021 | WMO, GWP-WA, NMHs, NHSs, other relevant |  |  |  |  | X
Outcome 2.2: Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons
Output 2.2.1 | Pilot testing for a number of areas over the basin (Figure 8) during the monsoon and dry seasons are performed | 2.2.1.1 Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list | ToR of the activity Mission reports Lists of the pilot tests areas | VBA | WMO will prpeare the overall concept note of the pilot testing. This will be tested end of next year in order to use the updated VOLTALARM system | VBA will have meeting in the 10 sites to inform them about the activities as well as to identify relevant staekholders in each of the sites for the actual pilot testing | GWP-WA will provide support in the finalization of the concept note | WMO, GWP-WA, NMHs, NHSs, other relevant |  |  |  |  | X
Output 2.2.3 | Development and implementation of community based flood and drought management |  | Concept Note Presentation supports workshop reports | VBA | WMO will prepare the concept note with the activities to be implemented in one community each of the 10 sites identified within the targeted countries WMO will also provide 6 low cost sustainable Hydro-Met stations for each community and overall do the monitoring and evaluation. | VBA will help in selection of one community (highly risk to floods or drought) based on the report developed under activitiy 1.1.1.4. BF-Flood Ghana-Flood Mali-Drought Cote d'Ivoire- Drought Benin-Flood Togo-Flood | Country Water Partnership(CWP) will implement activities describe in concept note in each of the communities identified and full funds to be transferred to them | WMO, GWP-WA, NMHs, NHSs, other relevant |  | X | X | X | X
Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions
Output 2.3.1 | Knowledge and capacity development using the Flood Green Guide (FGG) | 2.3.1.1 Development of Training Curriculum of the FGG/IUCN Standard | Training Curriculum of the FGG/IUCN standards | WMO | WMO will develop the training curriculum and also the process of involving the National stakeholders linking with output 1.2.3 | VBA will provide support in disseminating and involving National stakeholders | GWP-WA will support WMO and VBA in organizing activities at the National/local level | GWP-WA, VBA, WWF/ IUCN | X | X |  |  |  | 0
|  | 2.3.1.2 Organize dedicated short courses (at least one per country) on the FFG approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management 2.3.1.3: Collect feedbacks from the workshop participants on their views and perception of FGG tools | Concept Note Presentation supports Workshop reports Training Curriculum of the FGG adapted | WMO | WMO will prepare the training modules on IUCN Nature based standards and as well as contents of the workshops including feedback mechanism from the participants
|  |  |  | VBA | WMO will provide technical support in the facililating the workshop together with VBA and GWP-WA team | VBA will prepare concept note together with WMO and organize two workshop before September 2021 Other 4 workshop will be done after Septemeber 2021 | GWP-WA will provide support in organizing workshops at each country of the Volta Basin | National/Regional and other project partners involved in the environmental and ecosystem services in each of the Volta Basin countries |  | X | X | X | X
[10 empty] | X | X | X | X
Output 2.3.2 | Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | 2.3.2.1 Finalization of Training Manual for mainstreaming gender in the E2E-EWS-F and flood management after review from expertise groups (E2E-EWS-F and Gender) such as OPACHE, ICIMOD etc. | Training Manual for mainstreaming gender in the E2E-EWS-F and flood management reviewed | WMO | WMO is currently developing the Training Manual and final draft version will be available in January 2021 | Review the final draft version | Review the final draft version | GWP-WA, VBA, ECOWAS/EGDC, OTHER RELEVANT, CAP-NET, | X | X | X
|  | 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | Concept Note Presentation supports Workshop reports Training Manual for mainstreaming gender in the E2E-EWS-F and flood management adapted | GWP-WA Before June 2021- Organize two workshops (cost for first two National workshops) | WMO will develop the concept note of the training workshop in English and share it to the VBA and GWP-WA to translate it in french. 2) WMO will also participate at atleast two training workshops to ensure activities are following the training manual. | VBA will provide support in information dissemination and support in organizing the workshop at the National level | GWP-WA to prepare the concept note and through their gender expert will translate the content of the global training manual into workshop materials with local case studies (as highlighted in the facilitator guide of the training manual) Atleast organize and conduct two National workshops (with the participants highlighted in the concept note) before July 2021 | NMHSs,civil protection, communities (women groups or asosciation, youths, elderly, etc) |  | X | X | X | X
|  | 2.3.2.3Collect feedbacks from the workshop participants on c on mainstreaming gender in E2EEWS-F and IFM with other stakeholders | [7 empty] | X | X | X | X
Component 3: Strengthening policy and institutional capacity for integrated flood and drought management at the local, national and transboundary levels
Outcome 3.1 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin.
3.1.1 | The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 3.1.1.1 Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | WMO will be consulted in the study process with Concept note as well as methodology to be conducted. Overall monitoring and evaluation will be carried out WMO provide support in the desk study and review the documents together with VBA and National stakeholders | VBA will develop the concept note and prepare the methodology of involving regional, National and local stakeholders(Meteorological, Hydrological, Civil protection, other ministeries involved in the management of the floods and drought events) to carry out study | GWP-WA will provide support in the study or review as highlighted in the cocnept note | GWP-WA, WMO, NMHs, NHSs, other relevant | X | X | X | X
|  | 3.1.1.2 Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts |  | VBA |  |  |  | GWP-WA, WMO, NMHs, NHSs, other relevant | X | X | X | X
|  | 3.1.1.3 Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies |  | VBA |  |  |  | GWP-WA, WMO, NMHs, NHSs, other relevant | X | X | X | X
3.1.2 | Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields (health, agriculture etc.) | ToR of the study National consultation reports Study report including i) the gaps and needs in policies and plans, and the key long-term strategies for floods and drought management; ii) recommendation at national level and needs for interconnection with transboundary policies | GWP-WA |  |  |  | VBA, WMO, NMHs, NHSs, other relevant | X | X | X
|  | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans, and to highlight the key long-term strategies for floods and drought management |  | GWP-WA/VBA |  |  |  | WMO, NMHs, NHSs, other relevant |  |  | X |  |  | Vu la nature de l'activté (appui à la mise en œuvre des instruments politiques des pays membres ABV) , un co-leadership (ABV-GWPAO) serait une expérience inédite pour sa mise en œuvre
|  | 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies | [5 empty] | WMO, NMHs, NHSs, other relevant |  |  | X
|  | 3.1.2.4 Present the recommendations to the policy-makers and ministries | Presentation and communication support Workshop report to adopt the recommandation | GWP-WA |  |  |  | VBA, WMO, NMHs, NHSs, other relevant |  |  | X |  | X
Note on E69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As the risk maps will be developed in the support of National partners, the action plan will provide necessary management and prevention plan to the Countries.
Note on D73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 32000+195000=227000