## INDICATORS TABLE VFDM
Indicator Table-PROJET VFDM
[7 empty] | Activity Completion timeline | [8 empty] | to be filled by the VFDM Implemeting Partner
COMPONENT | INDICATEUR DE PROJET | OUTCOME/RESULTAT | INDICATEURS DE RESULTATS | OUTPUT/EXTRANTS | INDICATORS | CIBLE | Year 1 | Year 2 | Year 3 | Year 4 | ACTITVITIES | INDICATEURS D'ACTIVITES | TARGET | SOURCE DE VERIFICATION | BASELINE | Year 1 | Year 2 | Year 3 | Year 4 | Risks/Assumptions/Challenges
Component 1: Assessment of the VCERs, development of the floods and drought risk maps (pluvial and fluvial) and integration of climate scenarios into the action plans. | • Degree of improvement in populations’ resilience to floods and drought events | Outcome 1.1 Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms | Development of Flood and Drought risks maps for the Volta Basin region | Output 1.1.1 Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | Percentage of baseline information on vulnerabilities, capacities, exposure and risks will be made available for the Volta Basin region | [5 empty] | Activity 1.1.1.1 Conduct a desk study (compilation of existing evidence-based past data (topographic maps, satellite images etc.), studies of extreme events, reports of disasters, etc.) and field visits to gather available information on VCERs and identify gaps or additional needs. | Number of desk study and field visit conducted Number of Agencies consulted Number of women consulted | 1 desk study per country; 1 field visit per country | National consultation report ; semestrial and annual report, PPR | 0 (No deskstudy completed) Number of women consulted are very few
[11 empty] | Activity 1.1.1.2 Develop an action plan to complement gathered information on the VCERs | Number of actions plans developped | Action plan for each country developed with recommendations | National Consultation report, Monitoring report, semestrial and annual report, PPR | 0 (Transboundary/National level EWS action plan is not available)
[11 empty] | Activity 1.1.1.3 Organize meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | Number of meeting conducted; Numbers of participant; number of young and women participats | one workshop per country Atleast 20 participants from 5 or more agencies/organization Atleast 50% should be women participants | Meeting/workshop technical report, semestrial and annual report, PPR | 0 ( National level consultation through workshops for flood and drought EWS was not conducted in last 3 years)
[11 empty] | Activity 1.1.1.4 Conduct pilot field studies (focus group discussion and semi-structured interviews) with communities to identify the multi-dimensional drivers of vulnerability and risk (social, economic, ecological, cultural, political and infrastructural determinants of vulnerability) in the Volta Basin areas highly exposed to different hydro-meteorological hazards | Numbers of pilote field studies conducted Number of stakeholders/beneficiares consulted Number of women and youths consulted | 7-10/per country | Pilote studies reports,semestrial and annual report, PPR | 0 (studies to understand community vulnerabilities and capacities were not conducted in last 4-5 years)
[11 empty] | Activity 1.1.1.5 Draft the field studies reports and the Volta-atlas | Number of field studie report available; Number of volta atlas Information visulaized on the web-based EWS | 1 field studies report/country; 1 volta atlas Information of the study sites are visualized on the web-based EWS | Pilote studies reports ; Volta atlas | 0(community level study report are not available for floods and drought related viulnerabilities in last 4 years)
|  |  |  | Output 1.1.2 Database of VCERs, floods and drought related risk maps are developed | Progress in terms of developing the database and risk maps (zones) on VCERs of Volta Basin (Percentage of basin surface area) | [5 empty] | Activity 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise at the VBA observatory, the NMHSs services and other relevant services (e.g. Geographical Institute, Civil security, etc.). Purchase additional equipment if necessary | Number of specifics IT equipement and IT/GIS equipements currently at VBA observatory, the NMHS services. Number of additional equipments purchased Number of agencies consulted in each ccountry | Based on the National consultation and assessment (tbc): xx equiment available XX equipement purchased xx services provided | national report for the IT/Database need and capacities available, Purchase report, Invoice, Physical availability of equipment | xx specifics IT and IT/GIS equipment currently available;
[11 empty] | Activity 1.1.2.2 Create the Volta Basin information exchange IT network by connecting the VBA observatory and the national services | Nomber of Volta Basin's and National IT network and Database architecture design | 1 IT network and Database architecture available for each country and VBA | Country IT network architecture report | 0 (VBA and National IT and Database network architecture are not available)
[11 empty] | Activity 1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | Numbers of functionnal and operational database linked with the existing database created | XX equipement purchased atleast 5 staff trained in eahc country for the Database management and IT related | linked Database availablity in each country | 0(Centralized/National database is not available in each country)
[5 empty] | The data from different countries will be made compatible highlighting the missing data and information of respective countries | [5 empty] | Activity 1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | Number of functional and operational webbased flood and drought risk map developed Number of technciains trained Number of training sessions carried out Number of Agencies consulted and data and information shared | Development of floods and drought risk map for the Volta Basin region | Web-based flood and drought risk availability under the VoltAlarm EWS | One existing maps in ghana (funded by world bank) -Other National level maps and data available -Volta Basin floods and drought risk maps are not available
[11 empty] | Activity 1.1.2.5 Assign roles and responsibilities to the agencies and organisations forming a task team to regularly complement and improve the database and risk maps and also to monitor and report on the new updates. | Number of staffs assigned and responsabilities plan available on complementing the database developped | atleast 2 staff in each country and 1 VBA staff assigned and responsabilities plan available | Report; assignment and responsabilities plan, semestrial and annual report, PPR | 0 (Volta Basin level floods and drought risk maps are not available and staffs are not available for developing and updating it)
|  |  |  | Output 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Number of workshops are organized for the dissemination of knowledge on VCERs and Flood and Drought risk maps | [5 empty] | Activity 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps | Numbers of online and face-to-face training workshop for local professionnel organised; Number of local professionnel reinforced Numberof women participants trained | atleast 2 training workshops per country | Training workshops/meetings reports; semestrial and annual report, PPR, | 0 (National staff trainings for risk maps development are not carried out)
[11 empty] | Activity 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement. | Numbers of joint workshops organised on VCERs and risk maps | 1 regional workshop organised | Joint workshop reports; semestrial and annual report, PPR | 0 (regional workshop to presene the risk maps processes and methodology are not carried out at the regional level)
[5 empty] | Number of women trained | [5 empty] | Activity 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries, to discuss the potential indirect risks that could arise (involuntary resettlement, protection of natural habitats, conservation of biological diversity, public health, physical and cultural heritage, lands and soil conservation) and to identify safeguard actions which will help minimizing those potential negative impacts. | Number of sensibilisation's materials developed and shared with the communities | 3 sensibilisation materials developed and shared with them | Materials developed and shared, Activity report; semestrial and annual report, PPR Images captured of risk maps posters | risk maps and risk knowledges are not delivered to communities
|  |  |  | Output 1.1.4 Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | Progress in the development of the VCER and Flood and Drought risk maps report | [5 empty] | Activity 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps for the stakeholders and Adaptation Fund project technical committee | number of technical report produced on VCERS and risk maps added value, success and challenges | one technical report per country | technical report prepared and shared with the stakeholders | No report is available for the risk maps and VCERS database added value
[11 empty] | Activity 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) | Number and type of raising public awarness documentatton devellopped/ Number of people affecteded by these document | 3 types of raising public awareness developped; 10 raising public awareness documetation developped | Raising public awareness, Activity report; semestrial and annual report, PPR | 0 (public awareness materials are not available)
|  | Outcome 1.2Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment) into current practices and knowledge |  | Output 1.2.1:Scenarios for socio-economic and environment development along with the climate change projections are collected | Progress in acquiring data and information on socio-economic, climate change projections for developing future scenarios | [5 empty] | Activity 1.2.1.1 Gather all available information on climate change scenarios from best scientific studies and global databases for the Volta basin and select the most relevant datasets | Number of report enhancing climate data needs and available as well as synthesis of climate scenario change from best scientist review | 1 country report gathering all data are developed | Activity report; semestrial and annual report, PPR | 0 (climate scenarios information are not available for the Volta basin region)
| • Quantitative details for the reduced number of the deaths and damage to assets and environment | [9 empty] | Activity 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades | Number of report on gathered data and information on socio-economy covering the next decade for the socio economuc scenario | 1 country report focused on socio economics data and information scenario | Activity report; semestrial and annual report, PPR | 0 (socio-economic data and information are not available for the Volta basin region
[11 empty] | Activity 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 | Number of report with climate change and economics predictions organized | 1 report focused on socio economics predictions | Activity report; semestrial and annual report, PPR | 0
|  |  |  | Output 1.2.2Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | Progress in terms of analysis of qualitative or modelled data output | [5 empty] | Activity 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs using the future socio-economic and climate scenarios to determine changes in VCERs and risk maps | Numbers of run using socio economic and climate scenarios in covered area with hyological and hydraulic models | 1 series runs's report per country | Activity report; semestrial and annual report, PPR | 0 (climate scenarios results are not available for the Volta basin region)
[11 empty] | Activity 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes | Numbers of first qualitatives assessment of the evolution of VCER and risk map under future changes conducted on uncovered area by hydological and hydraulic models | 1 qualitative/quantative assessments per country | Activity report; semestrial and annual report, PPR | 0(climate scenarios results are not available for the Volta basin region)
[11 empty] | Activity 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios | Number of draft report developed | 1 report for the rVolta Basin regional is made available | Activity report; semestrial and annual report, PPR | 0 (future scenarios impact study is not available for the Volta Basin)
|  |  |  | Output 1.2.3Impact on environmental and ecosystem services indicators is evaluated for current and future scenarios | Progress in terms of impact assessment, designing measures and identification of actors | [5 empty] | Activity 1.2.3.1 Define indicators related to environment and ecosystem services (wetlands) conditions | Number of desk studies carried out Number of indicators related to environment and ecosystem services conditions | Volta Basin level report xx indicators defined | Activity report; semestrial and annual report, PPR | 0 (report related to the environmental and ecosystem services for the Volat basin is not available)
[11 empty] | Activity 1.2.3.2Collect and process information for various environmental indicators, | Number of data collection and proccessing activities Number of Agencies contacted for the data collection Number of responses received from the National Agencies | Data collection and processes tools and report available at the Volta basin level | Activity report; semestrial and annual report, PPR | 0(National Environmental and ecosystem or regional data and information for the Volta Basin are not available)
[11 empty] | Activity 1.2.3.3Select thresholds and carry out analysis for current and future climate scenarios | Numbers of current and future climate scenarios analysed | xx current scenario and future scenarios for the Volta Basin region | Activity report; semestrial and annual report, PPR | 0 (Current and future scenarios on ecosystem and environmental servicesfor the Volta Basin not available)
[11 empty] | Activity 1.2.3.4Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology | Number of areas identified to test the methodology | 2 or 3 areas for data collection and testing the methodology | Activity report; semestrial and annual report, PPR | 0(Data not available for ramsar sites)
[11 empty] | Activity 1.2.3.5Draft report with the methodologies and tools used for studying the impacts of environmental flow and experience of pilot tests. | Number of report developed on the ecosystem and environmental status and services impacts | 1 report per Volta Basin available (having Country level information) | Activity report; semestrial and annual report, PPR | 0 (report not available on the ecosystem and environmental status and services impacts for the Volta Basin region)
[11 empty] | Activity 1.2.3.6Drafting an integrated basin-wide wetland guidelines to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders. | Number of guidelines document developed Number of agencies reports are shared and feedback received | 1 guidelines for the Volta Basin region is made available | Guidelines document and activity report; semestrial and annual report, PPR | 0(Guideline documents are not available for the Vota Basin)
[11 empty] | Activity 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity | Number of workshops organized Number of stakeholders involved Numberrof women participants Bankable project proposal initiated or developed | One regional workshop conducted, Natioanl stakeholders attended the discussion; bankable project initaited or developed | Activity report; semestrial and annual report, PPR | 0(Project proposal at the National level are not available for the environmental and ecosystem services)
|  | Outcome 1.3:Risk management strategies in short, medium and long-term to be integrated into development plans (economic, social, environmental aspects) |  | Output 1.3.1Guidance documents for stakeholders are developed to raise awareness about the future scenarios | Guidance document on future scenarios for the Volta Basin region will be developed for the transboundary level | [5 empty] | Activity 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps development and future impacts on VCERs assessment with examples of implementation on high vulnerable urbans and agricultural areas | Number of guideline document developped and shared | 1 guideline document for the transaboundary level (with information at the National level is made available) | Activity report; semestrial and annual report, PPR | 0(Guideline documents are not available for the risk maps development)
[11 empty] | Activity 1.3.1.2 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) | Number and kind of communication materials with action developped | 10 means of commnication developed; 4 kinds of supplementary means of communication developed | Activity report; semestrial and annual report, PPR | 0(communication materials are not available for the risk awareness and management)
|  |  |  | Output 1.3.2Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | Number of workshops are organized for the dissemination of risk management strategies and action plan for their integration into development plans | [5 empty] | Activity 1.3.2.1 Organize trainings and workshops with stakeholders (representatives of communities, local policy-makers and decision makers) to disseminate the information on future climate and risk changes and to obtain additional qualitative input on potential impacts for social, economic and environmental development | Numbers of training and workshop for dissemination purposes in the communities | 4 communtiies in each country | Activity report; semestrial and annual report, PPR | 0(community awareness about the risk maps are not carried out)
[11 empty] | Activity 1.3.2.2Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments | Number of capacity building course for NMHSs developped | Capacity development courses developed and available for the NMHSs | Activity report; semestrial and annual report, PPR | 0(Capacity development courses are not available for the NMHSs)
[11 empty] | Activity 1.3.2.3Develop safeguard action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders | Number of safeguard action plan for risk management developped | 1 safegard action for the whole bassin | Activity report; semestrial and annual report, PPR | 0( risk management framework is not availbale for the Whole Volta Basin)
Component 2: Support to develop early warning systems for floods, and drought. Capacity development for strengthening knowledge and awareness related to climate change adaptation measures (Flood Green Guide and gender mainstreaming). | •Local /national agencies and communities are trained on climate change adaptation measures for floods and drought and mainstreaming of gender | Outcome 2.1Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Output 2.1.1Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | Number of meetings and consultation workshops organised and conducted to understand capacities and needs of the NHS and other stakeholders | [5 empty] | Activity 2.1.1.1Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) | Number participants identified and selected for the trainings | atleast 5 participants per country | Activity report; semestrial and annual report, PPR, Concept note shared and survey conducted | 0(Training curriculum for the Ntaional staffs are not available)
[11 empty] | Activity 2.1.1.2Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas | Number of training modules developed Number of staffs takes the e-learning courses Number of staffs provide training certificates | atleast 10 training modules are developed Atleast 5 Staffs from the Ntaional agencies take the courses and get certification | Training modules developed and accessed by the Participants, Activity report; semestrial and annual report, PPR | 0(e-learning training modules on floods and drought management is not available)
[11 empty] | Activity 2.1.1.3Organize the training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises | Number or training session organised at the transbondary level; number of participants | 1 transboundary training workshop conducted; atleast 5 participant per country | Activity concept note and workshop report; semestrial and annual report, PPR | 0 (Practical exercises on the management of floods and drought are not conducted with the National stakeholders)
|  |  |  | Output 2.1.2The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | Progress in the identification of need and procurement of the resources (equipment’s, staffs etc.) | [5 empty] | Activity 2.1.2.1Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | Report development on numbers and kinds of needs required and capacities available at the National level | xx kinds of need; xx need of specifics equipment or other facilities available or needed | Activity report; semestrial and annual report, PPR | 0 ( Information on existing capabilities and needs are not available)
[11 empty] | Activity 2.1.2.2 Buy, install and test the equipment needed to create and use the VoltAlarm EWS | Number and types of equipments bought; number of equipment installed and tested to create the VoltAlarm EWS | xx equipement bought; xx equipement installed | Activity report; semestrial and annual report, PPR | 0(EWS for the Volta Basin countries are not available)
[11 empty] | Activity 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Web-based EWS | Number of member of the operational team selected and trained Number of women participants trained | Atleast 3 people from eachof the six countries | Activity or training report t; semestrial and annual report, PPR, training concept note and participants lists | 0 (EWS operational training is not provided to the National services or at VBA)
[11 empty] | Activity 2.1.2.4 Write the operational manual including procedures and responsibilities | Number of operationnal manual written | One operational manual is developed and shared with the National services | Operational manual developedt; semestrial and annual report, PPR | 0 (Operational manual is not available for the EWS )
[11 empty] | Activity 2.1.2.5 Run and maintain the VoltAlarm system | Web-based VoltAlarmSystem is designed and developed | web-based EWS is available for the National services to use | Web-based EWS accessable and report; semestrial and annual report, PPR | 0 (EWS is not available for the Volat basin countries)
|  |  |  | Output 2.1.3The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | Percentage of data collection, storage and management of each country | [5 empty] | Activity 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) | Number of Inventory report of the gauging station with real time data transfer; Number of gauging stations with realtime data transfer Number of automatic or manual stations with their locations | 1 report per country; xx gauging station with data transfer processes | Activity report; semestrial and annual report, PPR | 0(List of gauging stations are not available for the each country)
[11 empty] | Activity 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data | Number of field/desk study planned and organized | 1 field visits in each country is conducted to meet the stakeholders and visit sites | Activity and Misison report; semestrial and annual report, PPR | 0 (Hydro-meteorological data and information are not available for the Volta basin countries)
[11 empty] | Activity 2.1.3.3Develop the database of hydro-meteorological parameters, or interconnect with existing platforms | Numbers of databases of hydr-meterological parameters updated or developped | National Database is developed or updated with the Hydro-Meteorlogical data and information from National or Globally available | Activity report; semestrial and annual report, PPR | 0 (Hydro-Met database is not regularly updated and shared)
[11 empty] | Activity 2.1.3.4Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards | Numbers of training organised in each country Numbe rof women participants invited for the trainings | 1 National training conducted for the NMHSs staff | Activity report; semestrial and annual report, PPR | 0 (National training for NMHSs staffs are not organized)
|  |  |  | Output 2.1.4Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | Progress in the development of thresholds levels for Floods and Drought risks linked with the environmental thresholds | [5 empty] | Activity 2.1.4.1Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas | Number of map with boundaries subbasin ans highly vulnerable areas | Volta Basin maps and vulnerbale areas are presented in the web-based EWS | Activity report; semestrial and annual report, PPR | 0 (Volta Basin maps are not updated with vulnerable and risky zones)
[11 empty] | Activity 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives supported by evidence-based experiences | Number of report on defining threshold for flood and drought events with the NMHSs | xx NMHSs involved for the threshold seelction and markings | Activity report; semestrial and annual report, PPR | 0 (Thresholds for flood and drought periods are not defined at the National level)
[11 empty] | Activity 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events | Number of areas identified; number and levels of thresholds per area close to gauging station are proceesed | number and levels of thresholds per area close to gauging station are defined for warnings | Activity report; semestrial and annual report, PPR | 0 (Thresholds for flood and drought periods are not defined at the National level for the areas close to the gauging stations)
[11 empty] | Activity 2.1.4.4 Link the environment threshold with the threshold of flood and drought | Number of algorithm Linked environemental threshold with the flood or drought thresholds | Number of flood and drought warnings are provided based on the environemntal thresholds | Activity concept note and report; semestrial and annual report, PPR | 0 (Flood and drought warnings are not issued with the Environmental thresholds or status)
|  |  |  | Output 2.1.5The procedure for producing impact-based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | Percentage of operationalization of Floods and Drought forecasting at the local and regional centres. | [5 empty] | Activity 2.1.5.1For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) | Number of Procedures developped to use the outputs of the existing models within the network of centers producing VoltAlarm | One procedure designed for the Volat basin region | Activity report; semestrial and annual report, PPR | 0 (procedure and connection with the existing models and platofrm are not available)
[11 empty] | Activity 2.1.5.2For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events | Number of complex of charts and graph /points develpped for areas covered with hydrological models for floods and drought forecasts and warning | one complex of chart Floods and drought indictor or reporting points are developed | Activity report; semestrial and annual report, PPR | 0 (floods and drought indicators are not available)
[11 empty] | Activity 2.1.5.3Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas | Number of software designed and developed | one Software is available and connected to the VolAlarm EWS | Activity report; semestrial and annual report, PPR | 0 (Warning levels are not based on Hydro-met Models at the National levels)
[11 empty] | Activity 2.1.5.4Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory | Number of interface developped to gather all individual system and connect with the VOLTALARM EWS | Interface with the existing warning levels are available for use | Activity report; semestrial and annual report, PPR | 0 (Interface with existing information are not available for use)
|  |  |  | Output 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | Progress in the design and development of the early warning dissemination tool | [5 empty] | Activity 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 11 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) | Concept note is prepared Numbers of consultation carried out Number of women participants involved for onsultations and decision-making | 1 per country | Activity report; semestrial and annual report, PPR | 0 (Co-design through participatory approach is not followed)
[5 empty] | Percentage of the population (men, women, elderly, and youths) understanding the added-value of the early warning system | [5 empty] | Activity 2.1.6.2 Develop and test the web-based dissemination interface | Number of webbased disemination interface is developed and tested with the feedback of womens, elderly etc. | Updated webbased dissemination interface is available for use | Activity report; semestrial and annual report, PPR | 0 (community consultations in the design and developemnt of EWS are not carried out regulalry)
[11 empty] | Activity 2.1.6.3 Write the user guide to convey all available knowledge on the interface to the various groups of users (forecasters, IT staff, decision-makers, etc.) | Number of userguides designed | xx User guide made for the Volta Basin countries | Activity report; semestrial and annual report, PPR | User guides are not available for the users of the EWS
|  |  |  | Output 2.1.7Knowledge and awareness about VoltAlarm are increased within the user groups. | Number of workshops are organised and conducted to develop capacities of the participants | [5 empty] | Activity 2.1.7.1Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS | Number of training and capacity developement workshop organized with the NMHSs professionals Number of women participants involved | one regional workshop is conducted | Concept note and workshop technical report; semestrial and annual report, PPR | Trainings on the usage of the EWS are not carried out regularly with the users
[5 empty] | Percentage of the population understanding the added-value of the early warning system | [5 empty] | Activity 2.1.7.2 Gather feedbacks, suggestions and scope for improvements from the workshop participants | Number of feedback and suggestion synthesis/reports from the Users | Feedbacks and recommendations analysed and incorporated | Activity report; semestrial and annual report, PPR | 0 (User feedbacks are not taken and used in the improving the EWS system)
[11 empty] | Activity 2.1.7.3 Organize a workshop to discuss with the trained participants how similar risk maps and early warning systems can be developed for areas outside of the Volta Basin | Number of workshop organized Number of women participants involved | one regional workshop together during the activitiy 2.1.7.1 are conducted | Activity and workshop report; semestrial and annual report, PPR | 0(Scaling up of products and tools are not carried out)
|  | Outcome 2.2Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Output 2.2.1Pilot testing for a number of areas over the basin (Figure 8) during the monsoon and dry seasons are performed | Progress in the pilot testing (identification and selection of pilot tests, monitoring during the floods and dry season etc.) of forecasting and EWS | [5 empty] | Activity 2.2.1.1Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list presented in Table 7 | number of pilots test areas identifed and selected Number of stakehodlers informed and engaged Number of women participants are mobilized | Pilot testing in 10 selected sites are conducted | Activity and consultation report; semestrial and annual report, PPR | 0 (Pilot testing of the EWS in the sites of the Volat basin are not carried out)
[11 empty] | Activity 2.2.1.2Organize meetings on each of the pilot areas to assign the roles and responsibilities of the different groups of stakeholders during the tests and present the coordination and collaboration mechanism enabling first responders to receive and use efficiently the early warning information | Number of meeting; synthesis document of role and responsabilities Number of women and youth participated | Atleast one meeting is conducted at each of the pilot sites; 1 meeting document is available per site with coordination mehchanism with roles and repsonsibilities | Activity report for each pilot sites; semestrial and annual report, PPR | 0(Local coordination and collaboration mechanism are not available at the local level)
[11 empty] | Activity 2.2.1.3Identify the good practices, challenges and limitations of products and services during the Flood and Drought events at each of the pilot testing locations | synthesis of good practies, challenges and limitation | 1 report per pilot sites is made available | Activity report; semestrial and annual report, PPR | 0(good practices, challenges and limitations of the flood and drought events for the pilot sites are not available
[5 empty] | Participation of various actors and stakeholders working for Floods and Drought management | [5 empty] | Activity 2.2.1.4Raise awareness about the pilot testing using multi-media channels | Number of awaress posted on multimedia channels; number of multimedi channels used | 3 multimedia channel used (facebook. Email communication) | Activity report; semestrial and annual report, PPR | 0(awareness materials are not available for the pilot sites)
[11 empty] | Activity 2.2.1.5Develop an action plan to further improve products and services after the pilot testing | Action plan for the pilot sites Consultation with the stakeholders Number of women consulted | Action plan for each pilot sites developed with recommendations | Activity report; semestrial and annual report, PPR | 0(Action plan are not available for the pilot sites. So after pilot testing during floods and dry period, the action plan will be developed )
|  |  |  | Output 2.2.2Feedback from the series of pilot testing is collected | Workshops are organised and conducted to develop capacities of the participants | [5 empty] | Activity 2.2.2.1Organize national consultative workshops (participants from local/national agencies involved in Floods and Drought management) to share the knowledge (new methodologies, concepts and tools for effective forecasting and dissemination of early warnings) from the pilots tests | Number of consultative workshop; number and origin of participants Number of women participate | 1 per country; atleast 20 participant per country | Activity concept note and technical workshop report; semestrial and annual report, PPR | 0(Consultation with the National stakeholders are not regularly carried out to identify the effectiveness and applicability)
[11 empty] | Activity 2.2.2.2Collect feedbacks from the workshop participants highlighting their views and perception of developed products and services | Number of synthesis report of workshop participant's feedbacks | Participants feedback reports are made available for the each country | Activity report; semestrial and annual report, PPR | 0
[5 empty] | Development of the communication material | [5 empty] | Activity 2.2.2.3Draft the series of reports on the experiences from the pilot testing and provide a summary of recommendations | Number of report to be prepared Number of women consulted | atleast one report with recommendations is made availabel for each pilot sites | Activity report; semestrial and annual report, PPR | 0 (experiences sharing with the beneficiaries are not carried out and recommendations are not avaiable)l
[11 empty] | Activity 2.2.2.4Develop communication materials to disseminate the results of the pilot testing and describe the added value of VoltAlarm | Number of communication material developped and shared Number of materials disseminated to the agencies and communities | atleast 3 to 4 communication types are available and disseminated to the stakeholders for the awareness | Activity report; semestrial and annual report, PPR | 0 (communictaion materials are not updated after every floods or drought events)
|  |  |  | Output 2.2.3Development and implementation of community-based flood and drought management | Progress in the identification and implementation of the local systems | [5 empty] | Activity 2.2.3.1Conduct participative community consultations to identify and select the appropriate local measures or equipments (non-structural preparedness tools such as early warning dissemination through loudspeakers and local radio, locally installed rain-gauge and river-gauge for hydrological data collection, marking of vulnerable houses for rapid response support, flood level marking plates to mark the previous year’s floods useful for future construction of resilient houses, simulation exercises, knowledge and awareness session on disaster risk reduction, ecosystem services, climate change adaptation and drought indicators). | Number of communities having CBFDM approaches and strategies Number of participatives community consultations organized Number of women, elderly and youths involved | Atleast one site in each country is provided with CBFDM approaches and strategies atleast two participatives consultations conducted in each of the sites selected | Activity concept note and consultation meeting reports; semestrial and annual report, PPR | 0 (Community based activties were not carried out in the selected communties)
[11 empty] | Activity 2.2.3.2Develop and install the local measures as identified with the communities under activity 2.2.3.1. | Number of local measures identified, developed and installed | atleast two to three preparedness measures are identified and developed/installed in the selected communtiies | Activity report; semestrial and annual report, PPR | 0(local preparedness measures are not available with the selected communities)
[5 empty] | Number of people contributing and benefiting from the local systems | [5 empty] | Activity 2.2.3.3Capacity building and formation of local community flood and drought management committees | Number of local capacity building training Numbe rof commitees formed with number of community representatives Number of womens and youths part of the committees | Atleast one committee is formed for the each of the selected communities | Activity report; semestrial and annual report, PPR | 0 (Local community based committees for the flood and drought management are not availbel for the selected committees)
[11 empty] | Activity 2.2.3.4Development of community-based flood and drought management manuals including safety and safeguard measures for preservation of natural habitats, land and soil conservation, biological diversity. | Number of community based management manual developped Number of consultations meeting carried out Number of field visits carried out Number of women, elderly and youths were consulted | community-based flood and drought management manual is developed for each community and shared with the local and national stakeholders | CBF(D)M manual for each community; semestrial and annual report, PPR Dissemination of the manual to the local and stakeholders | 0(community-based flood and drought management manuals are not available)
[11 empty] | Activity 2.2.3.5Organize meetings to share knowledge and experience of added-value of local measures or equipments | Number of meetings; number of participant (female, male and youngs) invited and involved | report of the knowledge sharing session is made available | Activity report; semestrial and annual report, PPR | 0(added value and experience sharing meetings are not organized)
|  | Outcome 2.3Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Output 2.3.1Knowledge and capacity development using the Flood Green Guide (FGG) | Number of workshops organised and conducted to develop capacities of the participants | [5 empty] | Activity 2.3.1.1 Develop the Training Curriculum of the FGG | Number of training culrriculum/modules developed Number of participants identified for the training Number of women invited and participate | FGG training is organized on-line and participants join the training and gainknowledge and skills of FGG Atleast 10 participants participate to the trainings | Activity report; semestrial and annual report, PPR, Concept note shared and survey conducted | 0(FGG training is never conducted with the Volta Basin stakeholders)
[11 empty] | Activity 2.3.1.2Organize dedicated short courses (at least one per country) on the FFG/IUCN standard approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management | Number of short courses organised; numer of participant (female, male and youths); number of countries srepresentative involved. Number of participants successfully conduct the trainings | 1 per country; atleast 20 participant per country attend the training workshop | Activity report; semestrial and annual report, PPR | 0 (IUCN Standard for Nature-based solutions for flood management are not carried out in the Volta Basin countries
[5 empty] | Number and type of local and national staffs selected for the training | [5 empty] | Activity 2.3.1.3Collect feedbacks from the workshop participants on their views and perception of FGG tools | Synthesis of feedbacks collected report is prepared for the each country | Feedback with sharing experiences will be made available | Activity report; semestrial and annual report, PPR | 0(feedbacks from the stakeholders are not available)
[11 empty] | Activity 2.3.1.4Recommend actions to increase the use of natural and nature-based solutions and environmentally friendly methodologies with the involvement of local population and aligning with the Adaptation Fund ESP principles | Number of recommended action and plan to achieve is prepared | recommendations and action plan report for each country is available | Activity report; semestrial and annual report, PPR | 0 (recommendations and action plan report for each country is not available)
[5 empty] | Number of stakeholders (women) trained | [5 empty] | Activity 2.3.1.5Conduct workshops to provide support for developing bankable project proposals (submission to the internal and external agencies in future) on natural and nature-based solutions for the flood events. | Number of workshop focused on development of bankable project Regional workshop is organized with the National stakeholders Number of women participants invited | Bankable project proposals are developed for each country or at regional level and ready for submission to the potential funding agencies | Concept note, Technical workshop and Activity report; semestrial and annual report, PPR | 0 (project proposals or implementation of project on nature-based solutions are not on-going at the regional or National level)
|  |  |  | Output 2.3.2Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management62 | Workshops are organised and conducted to develop capacities of the participants | [5 empty] | Activity 2.3.2.1Finalize the development of the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | Training manual for mainstreaming gender is drafted and review process is carried out | Training Manual for mainstreaming gender is made available and ready for adapting to the Volta Basin countries | Training Manual ; review comments from peer reviewers, semestrial and annual report, PPR | 0 (Training Manual for mainstreaming gender is not available)
[11 empty] | Activity 2.3.2.2Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | Number of workshops organized with the National and local stakeholders Number of women participants involved | Atleast one workshops in four countries (Benin, Togo, Cote d'Ivoire, Mali) and two workshops at Ghana and Burkina Faso are conducted | Concept note, Activity report;workshop report, semestrial and annual report, PPR | 0 (dedicated workshops for mainstreaming gender are not conducted in the Volta basin countries)
[11 empty] | Activity 2.3.2.3Collect feedbacks from the workshop participants on their views and knowledge sharing on mainstreaming gender in E2E-EWS-F and IFM with other stakeholders | Synthesis of feedbacks collected report is prepared for the each country Survey form is developed and shared with the participants | Feedback report from each workshop is made available | feedback report from each workshop; semestrial and annual report, PPR, filled survey response | 0(feedback of the workshops are not available for the mainstreaming gender)
[5 empty] | Percentage of women with physical, social, political and economic empowerment | [5 empty] | Activity 2.3.2.4Recommend actions that would improve the participation of women into flood management and early warning | Number of recommended action is prepared with consultations of participants | Recommendation and action plan are developed for each country and made available | recommendation and action plan report; semestrial and annual report, PPR | 0 (recommendations and action plan for mainstreaming gender are not available for the Volta Basin countries
Component 3: Revision of the transboundary governance plans, policies and guidelines and their links with the national climate | Percentage of households (including female-headed households) with improved livelihoods or economic benefits | Outcome 3.1Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin. |  | Output 3.1.1The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | Desk study and meetings are organised and available baseline data and information is shared as supporting details | [5 empty] | Activity 3.1.1.1Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management | Number of desk studies and meeating organised Number of stakeholders consulted Number of men and women participants consulted | 1 study report for the whole basin is made available with information for each country is provided | Desk study report and activity concept note ; semestrial and annual report, PPR | 0 ( report on the status of climate and future economic changes are not available)
[11 empty] | Activity 3.1.1.2Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts | Number of report prepared with strengths, gaps and needs | A report with strengths, gaps and needs are prepared for the each country | Activity report; semestrial and annual report, PPR | 0 (report with strengths, gaps and weaknesses are not available)
[5 empty] | Number of policies, plans and guidelines to be revised | [5 empty] | Activity 3.1.1.3Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies | Longterm action plan for strengthening resilience is prepared for each country | Longterm action plan for strengthening resilience is available for each country | Activity report; semestrial and annual report, PPR | 0(Longterm action plan for strengthening resilience is not available/prepared for each country
|  |  |  | Output 3.1.2Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | Number of workshops organised and conducted to develop capacities of the participants (decision-makers, policy-makers) | [5 empty] | Activity 3.1.2.1Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields (health, agriculture, ecosystem, forestry, soil and land management.) | Synthesis of the network description for each country is prepared | Network description for each country is made available | Activity report; semestrial and annual report, PPR | 0 (neetwork description and hierrachy are not available)
[11 empty] | Activity 3.1.2.2Organize and conduct national workshops to identify the gaps and needs in policies and plans with special attention on safeguard actions for minimizing direct and indirect risks arising from the project activities , and to highlight the key long-term strategies for floods and drought management | Number of national workshop are organized Number of stakeholders invited Numbe rof women participants invited | One National workshop in each country are conducted | Activity concept note and workshop report; semestrial and annual report, PPR | 0(policies and plans are not aevaluated for management of floods and drought at the Volta basin countries)
[5 empty] | Number of women participating in the workshops | [5 empty] | Activity 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies | feedbacks and recommandations are collected Survey form prepared and shared Number of participants provide response to the survey form | National level feedback and recommendation report is made available | Activity report; semestrial and annual report, PPR | 0 (recommendations and feedback on policies and plans are not available or provided by the National stakeholders)
[11 empty] | Activity 3.1.2.4Present the recommendations to the policy-makers and ministries | Number of recommandation prepared and presented to the policy makers Number of policymakers consulted Number of women policymakers are invited and consulted | recommendations to the policy makers are presented and review feedbacks are made available | Activity and recommendation report; semestrial and annual report, PPR | 0(recommendations are not shared and incorporated at the National level)
|  |  |  | Output 3.1.3Experiences of local communities on key long-term strategies for floods and drought management are collected | Progress in the organising meetings or consultation workshops at local level | [5 empty] | Activity 3.1.3.1Draft a report with evidence-based experiences at local level | A report with evidence based experiences is drafted or prepared with the desk studies or consultation of local stakeholders/communities | A national/regional report is made available | Activity report; semestrial and annual report, PPR | No report is available with the evidence-based experiences at the local level
[11 empty] | Activity 3.1.3.2Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. | Number of local workshop organized Number of women participants involved | Atleast 2 local workshops in each of the country are conducted to identify possible solutions and arrangements for improving socio-economic development | Activity and workshop report; semestrial and annual report, PPR | 0( local workshops in each of the country are not organized on possible solutions and arrangements for improving socio-economic development)
[5 empty] | Number of women, elderly, and youths consulted | [5 empty] | Activity 3.1.3.3Collect feedbacks and recommendation at local level and provide input on the needs for relationships to national policies | feedbacks and recommandation at local level are collected through interviews and focus groups dicussion Questionnaires and discussion tools are prepared | Recommendations and feedbacks at the local level are available | Activity report; semestrial and annual report, PPR | 0(feedbacks and recommendation information from the communities are not available or not updated)
|  | Outcome 3.2Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Output 3.2.1Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to risk reduction and EWS | Number of transboundary consultative workshop organised with the policy-makers and advisors | [5 empty] | Activity 3.2.1.1Organize and conduct workshops to disseminate the revised, or new, plans, policies and guidelines on climate adaptation measures in the Volta Basin. | Number of local workshop organized Number of women participants involved | Atleast one regional workshops is conducted with the stakeholders to present the new or revised plans, policies or guidelines | Activity concept note and workshop report; semestrial and annual report, PPR | 0(National or transboundary policies or plans are not updated based on consultations with the communities)
[11 empty] | Activity 3.2.1.2Collect feedbacks, suggestions and recommendations from the workshop participants on the links between activities of National Programmes and the Volta basin project | Feedbacks and recommandations are collected Survey form prepared and shared Number of participants provide response to the survey form | atleast 6 survey form or consultation reports are available from the Volta Basin countries | Activity and feedback/recommendations report; semestrial and annual report, PPR | 0(feedback and recommendations are not available and integarted into the existing National or transboundary plans and policies)
| •Policies and guidelines at national and transboundary level for flood and drought management are better integrated and action plans are developed. | [9 empty] | Activity 3.2.1.3 Identify roles and responsibilities of the individual organizations and define the coordination mechanism to improve the implementation of the climate change adaptation measures | A task team with roles and responsabilities idenfication and defining at the National level with the coordination mechanism | Roles and responsibilities of the National task team is made avaialble | Activity report; semestrial and annual report, PPR | 0(A task team is not available at each country of the Volta Basin)
|  |  |  | Output 3.2.2Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | Consultative meeting are organised so that new or existing plans, polices and guidelines on climate change adaptation and disaster risks management are integrated into the transboundary EWS. | [5 empty] | Activity 3.2.2.1Launch national consultations in the six countries to gather feedback on the effective coordination between national and transboundary policies in the framework of floods and drought management and climate adaptation | Numbers of national and regional consultations focused on coordination between national and transbondary policies and plans are organized Number of women involved in the consultations | National and regional consultations focused on coordination between national and transbondary policies and plans are conducted | Activity report; semestrial and annual report, PPR | 0(coordination and consultation with the National and regional entities are not carried out)
[11 empty] | Activity 3.2.2.2Draft a report with recommendations from the consultations | Numbers of reports with recommandations drafted | Reports with recommendations are available | Activity report; semestrial and annual report, PPR | 0(recommendations are not available and incorporated at the National/Transboundary level)
[11 empty] | Activity 3.2.2.3Organize the dissemination of the report to policy-makers | Number of dissemination sessions of the report to policy makers | one dissemination session with the local policy makers in each country | Activity report and dissemination strategy; semestrial and annual report, PPR | 0(updated policies and action plans are not shared with the local policy makers)
|  | Outcome 3.3A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Output 3.3.1Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Number of meetings organised with the communities and organizations | [5 empty] | Activity 3.3.1.1Conduct a desk study and consultation of local stakeholders to gather examples of best practices for flood and drought risk reduction and climate adaptation related measures | Numbers of deskstudy and consultation of local stackeholders organized Number of women consulted | atleast 12 communities consultaion are carried out | Activity report; semestrial and annual report, PPR | 0 (community-consultation to disseminate best practices are not carried out)
[5 empty] | Number of men, women, elderly, and youths consulted | [5 empty] | Activity 3.3.1.2Develop capacity building documentation for local communities with the help of the local stakeholders | Number of capacity builing documentation for local communities developped or prepared | atleast one capacity development materials are made available to the communities of the Volta Basin countries | Activity report and capacity development material; semestrial and annual report, PPR | 0(capacity development materials are not available)
[11 empty] | Activity 3.3.1.3Draft report on recommendations from local communities | Numbers of reports on recommandations from local communities are prepared | A report with recommendations from the local communities are made available for the regional level | Activity and recommendation report; semestrial and annual report, PPR | 0 (recommendation report are not available from the local communities)
|  |  |  | Output 3.3.2Collaboration with local communities and organizations in finalizing policies and procedures to manage risks and to adapt to climate change | Number of meetings organised with the communities and organizations | [5 empty] | Activity 3.3.2.1Prepare a framework of safeguard actions for community involvement on long term disaster risk reduction with local stakeholders | Numbers of frameworks of safeguard actions prepared for longterm DRR with local stakeholders | Local framework of safeguard action is made available for each countries | Activity report and framework document; semestrial and annual report, PPR | 0 (local framework for safeguard action is not available for each country)
[11 empty] | Activity 3.3.2.2Conduct community-based workshops with agencies, local communities and organizations to prioritize adaptation measures | Numbers of community based workshop organized to prioritize adaptation actiion Number of women invited and involved in the decision-making | atleast one community-based workshops are conducted in the each of the Volta Basin countries | Activity and workshop report; semestrial and annual report, PPR | 0(local workshops are not regularly conducted to prioritze the adaptation measures)
[5 empty] | Number of men, women, elderly, and youths consulted | [5 empty] | Activity 3.3.2.3Collect feedbacks, suggestions and recommendations | Feedbaacks sugestion and recommandation reports are prepared Feedback form is prepared and shared with the participants | feedback and recommendation report are available for each community worskshops | Activity and feedback report; semestrial and annual report, PPR | 0 (feedback and recommendations are not collected from the communities in the recent past)
[11 empty] | Activity 3.3.2.4Propose action plans at local and national levels to increase local participation | Number of action plan prepared at local and national levels to increase local participation | action plan for each countries for local participation is made available | Activity and action plan report; semestrial and annual report, PPR | 0(action plan to involve local communities are not available)