## Detailed WP 2020-2021
Detailed Workplan and Draft Budget- VFDM project Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali and Togo
Project No:
Project Name: | Integrating Flood and Drought Management and Early Warning for Climate Change Adaptation in the Volta Basin
Implementing Agency: | WMO
Executing Agency: | WMO/GWP-WAF/VBA
Source of funding : | Adaptation Fund
PMT-Project Management Team
Output | Expected Output Description | Activities under Output | Activity Occurrence | Sub Activity Occurrence | Type of expenditure | Main coordinator | Role of Executing entity (WMO) | Role of Executing entity (VBA) | Role of Executing entity (GWP-WA)
Component 1: Develop capacity and established frameworks at the local, national and regional levels to ensure risk informed decision-making | [9 empty] | Year I -2019 |  |  |  | Year II-2020 |  |  |  | Year III-2021 |  |  |  | Year IV-2022 |  |  |  | Year V-2023
Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms | [9 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2
Output 1.1.1 | Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | 1.1.1.1 Conduct a desk study and field visits (compilation of existing past data (topographic maps, satellite images etc.), studies of extreme events, reports of disasters, etc.) to gather available information on VCERs and identify gaps or additional needs | 1 |  | Desk study/field work | Main coordinator : WMO Technical implementation partner: CIMA CIMA will conduct the assessment with the WMO consultant and one of the project team members in each of the six countries. This will also serve as capacity building of the PMT to apply the assessment methodology in the following years. | Focal points of PMT provide support in the assessment preparation and be part of assessment team. Writing invitation letters to each country representative agencies (list of agencies to be prepared from the contributing sheet in the project proposal) informing about the assessment and support required follow-up to ensure various agencies are available (with required information to some extent) for the dates planned for the assessment in each country
|  | a) Desk study of existing information | 1 | a | Desk work | Review of existing information - 30 days | Ensure the Consultants receive information links, documents etc. | Ensure the Consultants receive information links, documents etc. | Ensure the Consultants receive information links, documents etc.
|  | b)planning for the consultation visits in the Six countries | 1 | b | Desk work | Prepare the methodology and assessment plan- 15 days | Provide support for the meetings and field visits (Liase with national agencies) | Provide support for the meetings and field visits (Liase with national agencies) | Provide support for the meetings and field visits (Liase with national agencies)
|  | c) Conduct meetings with the national agencies and field visits to the stations/offices in Burkina Faso, VBA and Mali | 1 | c | Field Visits | Carry out misssion two countries at a time 5 days preparation 7 days mission 5 days reporting | Part of the assessment team in BF, VBA | Part of the assessment team in BF, VBA and Mali | Part of the assessment team in BF, VBA
|  | d) Conduct meetings with the national agencies and field visits to the stations/offices in Ghana and Cote d'Ivoire | 1 | d | Field Visits | 5 days preparation 7 days mission 5days reporting | Part of the assessment team in Ghana | Part of the assessment team in CI | coordination support and other works (operational plan and communication guidelines)
|  | e) Conduct meetings with the national agencies and field visits to the stations/offices in Togo and Benin | 1 | e | Field Visits | 5 days preparation 7 days mission 5 days reporting | Overall coordination | coordination support and other work (operational plan and communication guidelines) | Part of theassessment team in Benin and Togo
|  | 1.1.1.2 Develop an action plan to complement gathered information on the VCERs and fulfill technical gaps (maps, satellite data requirements) | 2 |  | Desk work | CIMA+Consultant in close collaboration with the PMT
|  | a) prepare detailed assessment report of six countries and VBA | 2 | a | Desk work | 10 days | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments
|  | b) Identify gaps and needs for the Risk maps and E2E-EWS for floods and drought | 2 | b | Desk work | 4 days | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments
|  | c) Develop Action plan to complement gathered informations and fulfill technical gaps | 2 | c | Desk work | 5 days | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments | Contribute and support in review document of the assessments
|  | 1.1.1.3 Organize workshops/meetings with the relevant stakeholders working on risk management to disseminate results of the assessment, gaps and action plan. select priority areas for community consultations | 3 |  | Training/Workshop | PMT to lead workshop and present the findings CIMA+Consultant will support facilitation of the workshop GWP-WA through their CWPs will do the workshop arrangements. | CIMA and PMT will draft the concept note and presentations PMT team will prepare the participant list in each country and send out invitation
|  | Preparation for the workshops+ Logistical Arrangements- | 3 | a | Desk work | Concept Note and presentation-7 days | Prepare list of people to partcipate in the workshop in joint consultation of VBA and GWP-WA staff | Provide support to CWP and as well ensure national agencies are informed and invited | GWP-WA with their CWP organize workshop in the six countries
|  | Conducting two workshop countries at one time-BF and then Mali-3 days each | 3 | b | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | Ensure proper arrangements of workshop in Ghana and CI is carried out | VBA PMT staff to attend the workshopand lead the falicitation of the workshop supported by consultants | GWP-WA PMT staff to attend the workshop in BF and also ensure proper arrangements of workshop in Ghana and CI is carried out
|  | Workshops at Ghana and then CI-3 days each | 3 | c | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap Comments and Discussions points are noted | WMO PMT staff to attend the workshop in Ghana and lead the falicitation of the workshop supported by consultants | VBA staff to attend the workshop in CI and lead the falicitation of the workshop supported by consultants. Ensure proper arrangements of workshop in Benin and Togo is carried out | Ensure proper arrangements of workshop in Benin and Togo is carried out
|  | Workshop at Benin and then Togo-3 days each | 3 | d | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap Comments and Discussions points are noted | Preparation for the pilot field visits (1.1.1.4) | Preparation for the pilot field visits (1.1.1.4) | GWP-WA staff to attend the workshop and lead the falicitation of the workshop supported by consultants
|  | Reports of the Meeting-4 days | 3 | e | Desk work | Technical Reports-5 days | CIMA, Consultant and PMT to jointly develop the reports | Provide review and techncial support to the reports | Provide review and techncial support to the reports
|  | 1.1.1.4 Conduct pilot field studies (focus group discussion and semi-structured interviews) with communities to identify the multi-dimensional drivers of vulnerability and risk (social, economic, ecological, cultural, political and infrastructural determinants of vulnerability) in the Volta Basin areas highly exposed to different hydrometeorological hazards | 4 |  | Field Visits | Cerfe to prepare the tools, guidelines and lead pilot studies in two countries-5 comunities and show the methodology and train the local researchers pilot sites team-Cerfe, CIMA, WMO, VBA, GEP-WA and local researchers Later, provide remote technical support and follow-up with the local researchers in other pilot communities Cerfe to prepare the data report of each countries with community consultations and give it to CIMA PMT to attend pilot visits (one at a time) | Parallel in each countries if possible | Provide logistical support and arrangements including permission from local mayor etc. | Provide logistical support and arrangements including permission from local mayor etc.
|  | Carry out field visits in each country (for the region under the VB) for community consultations BF-15 communities Ghana-15 communities CI-5 communities Togo-10-communities Benin-8 communities Mali- 7 communities | 4 | a | Field Visits | CIMA- 2 days visit in two pilot sites of the one countries Demonstrate tool for data collection (GPS locations of vulnerable infrastructures, population etc), data management and later prepare vulnerability or local risk maps CERFE provide testing of methodology and tools in 5 sites | Participate in the pilot field visits carried out by Cerfe | Participate in the pilot field visits carried out by Cerfe | Participate in the pilot field visits carried out by Cerfe
|  |  | 4 | b | Field Visits | Cerfe with local researchers and partners to do field visits |  | Assist in the field visits and also participate with the team in 5 sites | Assist in the field visits and also participate with the team in 5 sites
|  |  | 4 | c |  | Local partners (CWP, Mayors staffs) cost- one local person at each site-250 USD per day- 2 days support at each site
|  |  | 4 | d | Software | Development of local risk maps for 60 sites | Provide CIMA with necessary data and information for developing the risks map | Provide CIMA with necessary data and information for developing the risks map | Provide CIMA with necessary data and information for developing the risks map
|  | 1.1.1.5 Draft the field studies reports and the Volta-atlas | 5 |  | Desk study/work | CIMA to prepare the atlas (local assessment, community consultations, Hydro-met hazards, local risk maps etc.) and integration with the national risk maps
|  | Consultation report with information on the multi-drivers of vulnerabilities | 5 | a | Desk study/work | CERFE in consultation with local researcher, CIMA and PMT | Review and provide guidance to the reports | Review and provide guidance to the reports | Review and provide guidance to the reports
Output 1.1.2 | Database of VCERs, floods and drought related risk maps are developed | 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise at the VBA observatory, the NMHSs services and other relevant services (e.g. Geographical Institute, Civil security, etc.). | 1 |  | Desk study/field work
|  | Carried out with national assessment of the six countries +VBA | 1 | c,d,e | Field Visits | Provide support for the meetings and field visits (Liase with agencies)
|  | 1.1.2.2 Create the Volta Basin information exchange IT network by connecting the VBA observatory and the national services | 6 |  | WMO IT expert, CIMA and PMT will Identify IT network configuration and Equipments (procurement) |  | Provide lists of agencies who needs to provide information (Hydro-met, PWD, etc.) as well liase with focal point agency where MCH and othe requipments will be installed or provided.
|  | Architecture of the network connection is developed(where it will be present, access to whom etc.) | 6 | a | Desk work | PMT will provide necessary support and information | Ensure national level focal points provide necessary information to the WMO IT expert and CIMA | Ensure national level focal points provide necessary information to the WMO IT expert and CIMA | Ensure national level focal points provide necessary information to the WMO IT expert and CIMA
|  | How database at the national level (as well local level) can be connected to the regional level (physically or using cloud ) | 6 | b | CIMA with the WMO IT Expert will carry out consultation | PMT will provide necessary support and information | provide support to the WMO IT and CIMA experts | provide support to the WMO IT and CIMA experts | provide support to the WMO IT and CIMA experts
|  | Number and Type of equipments to be purchased for developing database at national and regional level | 6 | c | CIMA with the WMO IT Expert will carry out consultation | PMT will provide necessary support and information | Prepare the list of the equipments to be ppurchased | Prepare the list of the equipments to be purchased | Prepare the list of the equipments to be purchased
|  | 1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 7 |  | Database (example: MCH)/software and server installation | Based on the findings from the assessment Main lead entity: WMO in support of PMT
|  | Procurement of the equipments and delivery in the countries | 7 | a | WMO to procure equipments based on their process and standards and as well train national and local staffs | PMT to ensure activities are carried out as needed and provide support to WMO IT expert and CIMA | WMO PMT staff to provide support in the procurement of the equipments | Coordination with the national agencies to prepare database and lists of people to be trained for MCH | Coordination with the national agencies to prepare database and lists of people to be trained for MCH
|  | MCH database to be installed and running (connecting with the exisitng database and information) | 7 | b | WMO IT expert to install MCH and CIMA to connect the multiple databases to DEWETRA interface for the risk maps | PMT will provide necessary support ensuring equipments reached the countries and authorities | Ensure procurement are done and MCH database is installed and participate to MCH training in Ghana | Ensure procurement are done and MCH database is installed and participate to MCH training in BF, CI, Mali and VBA | Ensure procurement are done and MCH database is installed and participate to MCH training in BF, VBA, Benin
|  | Data related to VCERs, Hydro-met are added from the six countries ( mainly for the region under Volta Basin and from existing projects ) to the MCH database | 7 | c | CIMA andWMO IT expert will provide technical support |  | Follow-up with countries to provide data and information for the risk maps | Follow-up with countries to provide data and information for the risk maps | Follow-up with countries to provide data and information for the risk maps
|  | 1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | 8 | Training/Workshop | Main coordination with WMO and NMHS Logistical-GWP-WA
|  | Connect or link already existing risk maps available at the national level (through diferent projects) for the Volta Basin region | 8 | a | CIMA to ensure information related to risk maps are merged and visualized under the Dewetra platform | PMT will liase with countries to check how the information could be reused | Ghana and CI | BF and Mali | Bein and Togo
|  | Training are provided to develop flood and drought risk maps for each country staffs Ghana-10 BF-10 Benin and Togo-8 CI and Mali-8 | 8 | b | CIMA to facilitate and train the staffs( demonstrating for pilot sites) 5 days preparation and 3 days trainings | PMT will identify potential participants and ensure necessary arrangements for the workshop | WMO-Ghana VBA and GWP-BF Benin and Togo-GWP-WA CI and Mali-VBA
|  | Trained participant provide more inputs to the areas for which the data is not completely available and also run Models or develop risk maps for that region | 8 | c | CIMA to provide technical support to the trained participants (through skype or in case needed, travel to the country)
|  | 1.1.2.5 Assign roles and responsibilities to the agencies and organisations to regularly complement and improve the database and risk maps | 9 | Technical Assistance | Main coordinating partners: WMO
|  | Roles and Responsibilities are defined and assigned to the national staffs | 9 | a | WMO with NMHS will define the roles and responsibilities for regularly improving the database | PMT will be consulted and taken support to prepare the list of staffs, agencies and for regular follow-ups
Output 1.1.3 | Capacity of stakeholders to use Floods and Drought risk maps is enhanced | 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps | 10 |  | Training/Workshop | CIMA will facilitate with WMO and trained staffs (NMHS and other agencies) NMHS to provide support in logistics (if not then CWP) | PT will be involved to provide support in the organizign the activities Project team to attend workshop (one at a time)
|  | Preparation for the workshops+ Logistical Arrangements- | 10 | a | Desk work | Concept Note and presentation- 3 days
|  | Conducting two workshop countries at one time-BF and then Mali-3 days each | 10 | b | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | BF, Mali-VBA
|  | Workshops at Ghana and then CI-3 days each | 10 | c | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | Ghana and CI-WMO
|  | Workshop at Benin and then Togo-3 days each | 10 | d | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | Benin and Togo-GWP-WA
|  | 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement | 11 |  | Field Visits |  | CWP to host the meeting with logistical arrangements (meeting place and minor catering)
|  | Preparation for the workshops+ Logistical Arrangements- | 11 | a | Desk work | Concept Note and presentation- 3 days
|  | Conducting two workshop countries at one time-BF and then Mali-3 days each | 11 | b | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | BF, Mali-VBA
|  | Workshops at Ghana and then CI-3 days each | 11 | c | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | Ghana and CI-WMO
|  | Workshop at Benin and then Togo-3 days each | 11 | d | Training/Workshop | Facilitation and discussions-6 days +2 days travel gap | Benin and Togo-GWP-WA
|  | 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries | 12 |  | Outreach and Communication | CIMA, Cerfe to facilitate the workshop along with PMT
|  | Development of brochure, pamphlets or banners | 12 | a | communication material | communication officer at the WMO or VBA or GWP-WA | PMT to provide technical support and review the work | PMT to provide technical support and review the work | PMT to provide technical support and review the work
|  | Distribution of the materials in the field visits and as well as adding soft copy in the project website | 12 | b | Field Visits | Local partners (Cerfe, CWP ) | PMT provide support in the field visits they attend and ensure materials are distributed | PMT provide support in the field visits they attend and ensure materials are distributed | PMT provide support in the field visits they attend and ensure materials are distributed
Output 1.1.4 | Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps for the stakeholders and Adaptation Fund project technical committee |  |  | Desk study/work
|  | 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) |  |  | Outreach and Communication
Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment,etc.) into current practices and knowledge
Output 1.2.1 | Scenarios for socio-economic and environment development along with the climate change projections are collected | 1.2.1.1 Gather all available information on climate change scenarios from best scientific studies and global databases for the Volta basin and select the most relevant datasets |  |  | Desk study/work | VBA/GWP-WAF/NMHS | WMO
|  | 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades |  |  | Desk study/work | VBA/GWP-WAF/NMHS | WMO
|  | 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 |  |  | Desk study/work | VBA/GWP-WAF/NMHS | WMO
Output 1.2.2 | Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs using the future socio-economic and climate scenarios to determine changes in VCERs and risk maps |  |  | Desk study/work
|  | 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes |  |  | Desk study/work
|  | 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios |  |  | Desk study/work
Output 1.2.3 | Impact on environmental indicators is evaluated for current and future scenarios |  |  |  |  | Main coordinator: WMO IUCN to provide necessary technical assistance and implementation support
|  | 1.2.3.1 Define indicators related to environment conditions | 3 |  | Desk study/work
|  | 1.2.3.2 Collect and process information for various environmental indicators | 3 | a | Desk study/work | IUCN will do desk study or meeting and ensure information related to environment and ecosystem are identified from their previous work in the Volta Basin | Support in accessing various concerened agencies and information at the national level | Support in accessing various concerened agencies and information at the national level | Support in accessing various concerened agencies and information at the national level
|  | 1.2.3.3 Select thresholds and carry out analysis for current and future climate scenarios | 12 | b | Desk study/work | IUCN and CIMA coordinate to carry out analysis for current and
|  | 1.2.3.4 Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology | 3 | c | Field Visits | IUCN will develop and carry out field visitis to test the methodology (1-2) | Ensure activities are carried out propoerly in consultation with national agencies | Provide support in the field visitis to one-two pilot sites and coordination and involvement of relevant agencies | Provide support in the field visitis to one-two pilot sites and coordination and involvement of relevant agencies
|  | 1.2.3.5Draft report with the methodologies and tools used for studying the impacts of environmental flow | 3 | d | Desk study/work | IUCN will prepare the draft report and present to the PMT and national agencies and later incorporate comments or suggestions from the reviewers | Technical review and share the report with agencies and other partners who can also review and provide guidance | Technical review and share the report with agencies and other partners who can also review and provide guidance | Technical review and share the report with agencies and other partners who can also review and provide guidance
|  | Activity 1.2.3.6 Drafting an integrated basin-wide wetland policy to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders. | 4 | e | Desk study/work and Consultation Workshops with Stakeholders | IUCN will prepare the draft report and present to the PMT and national agencies and later incorporate comments or suggestions from the reviewers | Technical review and share the report with agencies and other partners who can also review and provide guidance | Technical review and share the report with agencies and other partners who can also review and provide guidance | Technical review and share the report with agencies and other partners who can also review and provide guidance
|  | Activity 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity | 12 | c | Technical Assistance | VBA to do the logistical arrangement for the workshop in Ouagadougou IUCN will facilitate the workshop and present the findings, recommendations as well as the integrated basin-wide wetland policy 5 days-preparation 4 days- workshop 5 days-reporting | Ensure relevant agencies participate to the workshop from the six countries | VBA will organize the regional workshop (logistical arrangements)- 15 participants | Ensure relevant agencies participate to the workshop from the six countries
Outcome 1.3: Risk management strategies in short, medium and long-term to be integrated into development plans (economic, social, environmental aspects)
Output 1.3.1 | Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps development and future impacts on VCERs assessment with examples of implementation on high vulnerable urbans and agricultural areas |  |  | Desk study/work
|  | 1.3.1.2 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) |  |  | Desk study/work
Output 1.3.2 | Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 1.3.2.1 Organize trainings and workshops with stakeholders (representatives of communities, local policy-makers and decision makers) to disseminate the information on future climate and risk changes and to obtain additional qualitative input |  |  | Training/Workshop
|  | 1.3.2.2 Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments |  |  | Desk study/work
|  | 1.3.2.3 Develop action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders |  |  | Desk study/work
Component 2: Develop concrete adaptation and environmentally friendly actions with an integrated approach
Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities
Output 2.1.1 | Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 2.1.1.1 Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) |  |  | Desk study/work
|  | 2.1.1.2 Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas |  |  | Desk study/work and Field visits to perform need assessments at various locations of the Volta Basin region
|  | 2.1.1.3 Organize the training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises |  |  | Training/Workshop
Output 2.1.2 | The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | 1 |  | Desk study/work
|  | Carried out with national assessment of the six countries and VBA | 1 | c,d,e | Field Visits |  | Provide support for the meetings and field visits (Liase with agencies) | Provide support for the meetings and field visits (Liase with agencies) | Provide support for the meetings and field visits (Liase with agencies)
|  | 2.1.2.2 Buy, install and test the equipment needed to create and use the VoltAlarm EWS |  |  | Equipment/software
|  | 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Webbased EWS |  |  | Training/Workshop
|  | 2.1.2.4 Write the operational manual including procedures and responsibilities |  |  | Desk study/work
|  | 2.1.2.5 Run and maintain the VoltAlarm system |  |  | Equipment/software
Output 2.1.3 | The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) | 1 |  | Desk study/work
|  | Carried out with national assessment of the six countries | 1 | c,d,e | Field Visits |  | Provide support for the meetings and field visits (Liase with agencies)) | Provide support for the meetings and field visits (Liase with agencies) Support in developing the inventory | Provide support for the meetings and field visits (Liase with agencies) Support in developing the inventory
|  | 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data |  |  | Field Visits
|  | Carried out with national assessment of the six countries |  | c,d,e | Field Visits |  | Provide support for the meetings and field visits (Liase with agencies) | Provide support for the meetings and field visits (Liase with agencies) | Provide support for the meetings and field visits (Liase with agencies)
|  | 2.1.3.3 Develop the database of hydro-meteorological parameters, or interconnect with existing platforms |  |  | Desk study/work
|  | 2.1.3.4 Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards |  |  | Training/Workshop
Output 2.1.4 | Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | 2.1.4.1 Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas |  |  | Desk study/work
|  | 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives |  |  | Desk study/work
|  | 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events |  |  | Desk study/work
|  | 2.1.4.4 Link the environment threshold with the threshold of flood and drought |  |  | Desk study/work
Output 2.1.5 | The procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | 2.1.5.1 For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) |  |  | Desk study/work
|  | 2.1.5.2 For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events |  |  | Desk study/work
|  | 2.1.5.3 Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas |  |  | Desk study/work
|  | 2.1.5.4 Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory |  |  | Desk study/work
Output 2.1.6 | The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 10 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) |  |  | Consultation workshop
|  | 2.1.6.2 Develop and test the web-based dissemination interface | 7 |  | Desk study/work | DCP will provide the Dewetra Interface to visulize the risk maps (later the FF-EWS)
|  | Make available DEWETRA interface and connect with the MCH database | 7 | a | Equipment/software | Availability of the DEWETRA platform | Provide necessary support to DCP to ensure Dewetra platform is available (on cloud initially) and connected with MCH database | Provide necessary support to DCP to ensure Dewetra platform is available (on cloud initially) and connected with MCH database | Provide necessary support to DCP to ensure Dewetra platform is available (on cloud initially) and connected with MCH database
|  | 2.1.6.3 Write the user guide to convey all available knowledge on the interface to the various groups of users (forecasters, IT staff, decision-makers, etc.) |  |  | Desk study/work
Output 2.1.7 | Knowledge and awareness about VoltAlarm are increased within the user groups | 2.1.7.1 Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS |  |  | Training/Workshop
2.1.7.2 Gather feedbacks, suggestions and scope for improvements from the workshop participants
2.1.7.3 Organize a workshop to discuss with the trained participants how similar risk maps and early warning systems can be developed for areas outside of the Volta Basin
Outcome 2.2: Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons
Output 2.2.1 | Pilot testing for a number of areas over the basin (Figure 8) during the monsoon and dry seasons are performed | 2.2.1.1 Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list |  |  | Desk study/work
|  | 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities of the different groups of stakeholders during the tests and present the coordination and collaboration mechanism enabling first responders to receive and use efficiently the early warning information |  |  | Training/Workshop
|  | 2.2.1.3 Identify the good practices, challenges and limitations of products and services during the Flood and Drought events at each of the pilot testing locations |  |  | Field Visits
|  | 2.2.1.4 Raise awareness about the pilot testing using multi-media channels |  |  | Outreach and Communication
|  | 2.2.1.5 Develop an action plan to further improve products and services after the pilot testing |  |  | Desk study/work
Output 2.2.2 | Feedback from the series of pilot testing is collected | 2.2.2.1 Organize national consultative workshops (participants from local/national agencies involved in Floods and Drought management) to share the knowledge (new methodologies, concepts and tools for effective forecasting and dissemination of early warnings) from the pilots tests |  |  | Training/Workshop
2.2.2.2 Collect feedbacks from the workshop participants highlighting their views and perception of developed products and services
|  | 2.2.2.3 Draft the series of reports on the experiences from the pilot testing and provide a summary of recommendations |  |  | Desk study/work
|  | 2.2.2.4 Develop communication materials to disseminate the results of the pilot testing and describe the added value of VoltAlarm |  |  | Desk study/work
Output 2.2.3 | Development and implementation of community-based flood and drought management | 2.2.3.1Conduct participative community consultations to identify and select the appropriate local systems (preparedness tools) to be installed |  |  | Training/Workshop
|  | 2.2.3.2 Develop and install the local systems |  |  | Equipment/software
|  | 2.2.3.3 Capacity building and formation of local community flood and drought management committees |  |  | Training/Workshop
|  | 2.2.3.4 Development of community-based flood and drought management manuals |  |  | Desk study/work
|  | 2.2.3.5 Organize meetings to share knowledge and experience of added-value of local systems |  |  | Training/Workshop
Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions
Output 2.3.1 | Knowledge and capacity development using the Flood Green Guide (FGG) | 2.3.1.1 Development of Training Curriculum of the FGG |  |  | Desk study/work
|  | 2.3.1.2 Organize dedicated short courses (at least one per country) on the FFG approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management |  |  | Training/Workshop
2.3.1.3 Collect feedbacks from the workshop participants on their views and perception of FGG tools
|  | 2.3.1.4 Recommend actions to increase the use of natural and nature-based solutions and environmentally friendly methodologies with the involvement of local population |  |  | Desk study/work
|  | 2.3.1.5 Conduct workshops to provide support for developing bankable project proposals (submission to the internal and external agencies in future) on natural and nature-based solutions for the flood events. |  |  | Training/Workshop
Output 2.3.2 | Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | 2.3.2.1 Finalization of Training Manual for mainstreaming gender in the E2E-EWS-F and flood management after review from expertise groups (E2E-EWS-F and Gender) such as OPACHE, ICIMOD etc. |  |  | Desk study/work
|  | 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training NManual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. |  |  | Training/Workshop
2.3.2.3Collect feedbacks from the workshop participants on their views and knowledge sharing on mainstreaming gender in E2E-EWS-F and IFM with other stakeholders
|  | 2.3.2.4 Recommend actions that would improve the participation of women and vulnerable groups into flood management and early warning |  |  | Desk study/work
Component 3: Strengthening policy and institutional capacity for integrated flood and drought management at the local, national and transboundary levels
Outcome 3.1 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin.
3.1.1 | The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 3.1.1.1 Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management |  |  | Desk study/work
|  | 3.1.1.2 Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts |  |  | Desk study/work
|  | 3.1.1.3 Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies |  |  | Training/Workshop
3.1.2 | Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields (health, agriculture etc.) |  |  | Desk study/work
|  | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans, and to highlight the key long-term strategies for floods and drought management |  |  | Training/Workshop
3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies
|  | 3.1.2.4 Present the recommendations to the policy-makers and ministries |  |  | Meeting
3.1.3 | Experiences of local communities on key long-term strategies for floods and drought management are collected | 3.1.3.1 Draft a report with experiences at local level |  |  | Desk study/work
|  | 3.1.3.2 Organize and conduct local workshops to get a wider input of communities |  |  | Field Visits
3.1.3.3 Collect feedbacks and recommendation at local level and provide input on the needs for relationships to national policies
Outcome 3.2 Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies
3.2.1 | Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to risk reduction and EWS | 3.2.1.1 Organize and conduct workshops to disseminate the revised, or new, plans, policies and guidelines on climate adaptation measures in the Volta Basin. |  |  | Training/Workshop
3.2.1.2 Collect feedbacks, suggestions and recommendations from the workshop participants on the links between activities of National Programmes and the Volta basin programme
|  | 3.2.1.3 Identify roles and responsibilities of the individual organizations and define the coordination mechanism to improve the implementation of the climate change adaptation measures |  |  | Desk study/work
3.2.2 | Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | 3.2.2.1 Launch national consultations in the six countries to gather feedback on the effective coordination between national and transboundary policies in the framework of floods and drought management and climate adaptation |  |  | Training/Workshop
3.2.2.2 Draft a report with recommendations from the consultations
|  | 3.2.2.3 Organize the dissemination of the report to policy-makers |  |  | Desk study/work
Outcome 3.3 A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context
3.3.1 | Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | 3.3.1.1 Conduct a desk study and consultation of local stakeholders to gather examples of best practices for flood and drought risk reduction and climate adaptation related measures |  |  | Desk study/work
|  | 3.3.1.2 Develop capacity building documentation for local communities with the help of the local stakeholders |  |  | Desk study/work
|  | 3.3.1.3 Draft report on recommendations from local communities |  |  | Desk study/work
3.3.2 | Collaboration with local communities and organizations in finalizing policies and procedures to manage risks and to adapt to climate change | 3.3.2.1 Prepare a framework of actions for community involvement on long term disaster risk reduction with local stakeholders |  |  | Desk study/work
|  | 3.3.2.2 Conduct community-based workshops with agencies, local communities and organizations to prioritize adaptation measures |  |  | Field Visits
3.3.2.3 Collect feedbacks, suggestions and recommendations
|  | 3.3.2.4 Propose action plans at local and national levels to increase local participation |  |  | Desk study/work
Note on F14: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on F37: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on F38: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on F99: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on F105: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on F107: Author: CIMA will conduct with the WMO consultant and one of the project officers the country visits (WMOGhana, VBABF, CdI and Mali, GWPTogo, Benin) to carry out the country assessments liaising with NMHSs, Civil Defence, Agricultural ministries, Water Resources Authorities, other stakeholders. The methodology will be in line with the WMO CHy Guidelines for assessment of national needs and capabilities in E2E EWS and will be mainly performed by CIMA and the WMO consultant. The VBA/GWP/WMO POs will be empowered with the methodology applied, and support CIMA and WMO consultant in liaising with relevant counterparts and drafting the assessment reports. Coordination: WMO to ensure team coordination between the partners (VBA, GWP) and Support Base Partner (CIMA). VBA to ensure access in the 6 countries to their Focal Points/relevant ministries; GWP to ensure access to relevant stakeholders through the 6 CWPs; WMO to ensure linkages with the 6 NMHSs. Travel to be organized independently by each partner based on funds made available through the LoA.
Note on C146: Author: NEW ADDITION..Add in the final proposal

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only