## WPYear 3 and 4 VFDM
Final year workplan- Volta Flood and Drought Management project Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali and Togo
Project Name: | Integrating Flood and Drought Management and Early Warning for Climate Change Adaptation in the Volta Basin
Implementing Agency: | WMO
Executing Agency: | WMO/GWP-WA/VBA
Source of funding : | Adaptation Fund
Activity completed
On-going or about to completed
To be started
Output | Expected Output Description | Activities under Output | Expected Deliverables | Main coordinator | International and National Partners to be involved | Roles and responsibilities of 3 Partnes (WMO, VBA and GWP-WA) | Status | 2023 |  |  | 2024
[8 empty] | Quarter 2 | Quarter 3 | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
Component 1: Develop capacity and established frameworks at the local, national and regional levels to ensure risk informed decision-making
Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms
Output 1.1.1 | Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | 1.1.1.3 Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | Workshop reports Presentation and Communication supports National mission reports | GWP-WA | NMSs, NHSs, Geographic institute, Other relevant, Aghrymet, WASCAL |  | Completed
|  | 1.1.1.4 Conduct pilot field studies (focus group discussion and semi-structured interviews) with communities to identify the multi-dimensional drivers of vulnerability and risk (social, economic, ecological, cultural, political and infrastructural determinants of vulnerability) in the Volta Basin areas highly exposed to different hydrometeorological hazards | Methodology note / Guidelines Mission report | WMO | NMSs, NHSs CIMA, IUCN, CERFE, Other relevant
|  | 1.1.1.5 Draft the field studies reports and the Volta-atlas | Missions reports, Volta-Atlas | WMO | VBA, GWP-WA, NMSs, NHSs CIMA, Other relevant
Output 1.1.2 | Database of VCERs, floods and drought related risk maps are developed | 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise at the VBA observatory, the NMHSs services and other relevant services (e.g. Geographical Institute, Civil security, etc.). Purchase additional equipment if necessary | Methodology note Database Mission report | WMO | NMSs, NHSs CIMA, Geographic institute, Other relevant
|  | 1.1.2.2 Create the Volta Basin information exchange IT network by connecting the VBA observatory and the national services | Assessment and Reporting | VBA | OMM, GWP-WA, NMSs, NHSs CIMA, Geographic institute, Other relevant
|  | A) Concept note and tool to be developed |  | WMO | check concept note |  | Completed
|  | B) Data and Information collection through National focal points |  | VBA | National agencies IT/DB focal points to provide information through consultation |  | Completed
|  | C.1) Country assessment mission by WMO IT expert |  | WMO | Face-to-Face meeting with the National Agencies IT/DB focal points of Burkina Faso |  | Completed
|  | C.2) Organization of the mission in other four countries and applying the tool and methodology |  | VBA | Face-to-Face meeting with the National Agencies IT/DB focal points of 5 countries |  | Completed
|  | D) Architecture of the network connection is developed(where it will be present, access to whom etc.) for each country including How database at the national level (as well local level) can be connected to the regional level (physically or using cloud ) and Number and Type of equipments to be purchased for developing database at national and regional level |  | WMO | Review the draft report and add misisng information. Validate the report |  | Reports are finalized
|  | 1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | list and characteristics of equipments Calls for tenders Equipment installation report | WMO
|  | Procurement of the equipments and delivery in the countries |  | WMO |  | WMO through NMHS is leading the procurement, training and operation of the MCH Dataabase in the Six countries VBA and GWP-WA will continue to provide necessary support to WMO and National agencies in the establishment of the centralized databases | IT/DB report prepared and finalized by the National Agencies under activity 1.1.2.2 Procurement completed and trainign of the IT/DB expert to be completed by May 2023 | X
|  | MCH database to be installed and running (connecting with the exisitng database and information) |  | WMO |  |  |  | X
|  | Training to the Hydro-Met and IT/DB experts of each country |  | WMO |  |  |  | X
|  | Data related to VCERs, Hydro-met are added from the six countries ( mainly for the region under Volta Basin and from existing projects ) to the MCH database |  | WMO |  |  |  | X
|  | 1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | Concept note Workshop report, Maps, communication supports Mission report | WMO | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant
|  | Connect or link already existing risk maps available at the national level (through diferent projects) for the Volta Basin region |  | WMO | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant |  | Completed
|  | Concept note development, methodolgy and sharing with the National Focal points |  | WMO | VBA, GWP-WA, NMSs, NHSs Geographic institute, Other relevant |  | Completed
|  | Planning and Preparation of the Risk map development training |  | GWP-WA | NMSs, NHSs Geographic institute, Other relevant |  | Completed
|  | Training (2 days in each country) are provided to develop flood and drought risk maps for each country staffs Ghana-12 technical staffs BF-12 technical staffs Benin and Togo-8 technical staffs CI and Mali-8 technical staffs |  | GWP-WA | NMSs, NHSs Geographic institute, Other relevant |  | Completed
|  | Trained participant provide more inputs to the areas for which the data is not completely available and also run Models or develop risk maps for that region |  | GWP-WA and NFP participants | NMSs, NHSs Geographic institute, Other relevant |  | On-going
|  | 1.1.2.5 Assign roles and responsibilities to the agencies and organisations to regularly complement and improve the database and risk maps |  | WMO/VBA | NMSs, NHSs Geographic institute, Other relevant
|  | Lists of National level focal points and assigning roles and responsibilities |  | WMO/VBA | NMSs, NHSs Geographic institute, Other relevant | WMO will request the selected agecnies in each of the six countries to provide support in the assigning roles and responsibilities for continously updating the database | To be completed with the MCH database training during April-May 2023 | X
Output 1.1.3 | Capacity of stakeholders to use Floods and Drought risk maps is enhanced | 1.1.3.1 Organize training workshop for local professionals (hydrologists, disaster managers, GIS experts etc.) to convey knowledge and improve skills needed for using risk maps |  | WMO | NMSs, NHSs CIMA, Geographic institute, Other relevant
|  | Integrate information from the National trained staffs (preparing the shape maps on vulnerability and exposure) and provide remote assistance in the development of the risk maps |  | WMO | NMSs, NHSs CIMA, Geographic institute, Other relevant |  | completed
|  | 6 National workshop with same staffs to follow the work done after training under 1.1.2.4 (after 30-45 days) | Follow-up to 1.1.2.4 | GWP-WA- | NMSs, NHSs Geographic institute, Other relevant |  | completed
|  | Trained participant provide more inputs to the areas for which the data is not completely available and also run Models or develop risk maps for that region |  | GWP-WA NFP | NMSs, NHSs Geographic institute, Other relevant |  | completed
|  | WMO together will external consultants will integrate the vulnerability, hazards, exposure maps in the VOLTALARM EWS |  | WMO |  |  | completed
|  | 1.1.3.2 Organize joint workshops for stakeholders to deliver knowledge on VCERs and Floods and Drought risk maps of Volta Basin and to gather feedbacks and suggestions for improvement | Concept note, Workshop report, presentation and communication supports | GWP-WA | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant
|  | Regional workshop with staffs and communities individuals to follow the work done after training under 1.1.3.1 (after 30-45 days) | Follow-up to 1.1.2.4 and 1.1.3.1 | GWP-WA | NMSs, NHSs Geographic institute, Other relevant |  | completed
|  | 1.1.3.3 Take advantage of community meetings to raise awareness of a larger number of Floods and Drought risk maps’ beneficiaries |  | GWP-WA | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant
|  | Design and development of the risk maps (techncial contents) on the banner, maps to overcome for the National agencies offices and important risk areas in the Volta Basin |  | WMO | NMSs, NHSs Geographic institute, community representative |  | Completed
|  | Printing of the materials and delivering it to the National agencies and communities at risks |  | GWP-WA | NMSs, NHSs Geographic institute, community representative
Output 1.1.4 | Reports and communication documents on vulnerabilities, capacities, exposure and risks (VCERs) and Floods and Drought risk maps of the Volta Basin are available | 1.1.4.1 Produce technical report on the added value, success and challenges of VCERs and Floods and Drought risk maps for the stakeholders and Adaptation Fund project technical committee | Terms of reference, Technical report | WMO | GWP-WA, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant | Completed | completed
|  | Development of the risk maps guideline document to make better understand the risk areas and measures to take in case of floods and drought events |  | WMO | NMSs, NHSs Geographic institute, community representative | Completed | Completed
|  | 1.1.4.2 Develop documentation for raising public awareness (infographics, videos, mobile phone applications, educational tools for children and students, etc.) | Communication support Pedagogical materials elaborated | GWP-WA | OMM, VBA, NMSs, NHSs CIMA, Geographic institute, Other relevant | Available by the GWP-WA
Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment,etc.) into current practices and knowledge
Output 1.2.1 | Scenarios for socio-economic and environment development along with the climate change projections are collected | 1.2.1.1 Gather all available information on climate change scenarios from best scientific studies and global databases for the Volta basin and select the most relevant datasets | Concept Note Database Mission report | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant |  | Completed
|  | 1.2.1.2 Gather the data on input for socio-economic scenarios of the Volta Basin region over the next decades |  | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant
|  | 1.2.1.3 Organize the data on climate and socio-economic predictions for further integration with VCERs and risk maps developed under outcome 1.1 |  | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant
Output 1.2.2 | Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 1.2.2.1 For areas covered with hydrological and hydraulic models (White Volta, Oti for example) perform a series of runs using the future socio-economic and climate scenarios to determine changes in VCERs and risk maps | Concept Note Database Mission report | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant
|  | 1.2.2.2 For areas not covered with numerical models, carry out a first qualitative assessment of the possible evolution of VCERs and risk maps under future changes |  | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant
|  | 1.2.2.3 Draft report with the methodologies and tools used for studying the impacts of future scenarios |  | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, IUCN, Other relevant
Output 1.2.3 | Impact on environmental indicators is evaluated for current and future scenarios | 1.2.3.1 Define indicators related to environment conditions | Concept Note, methodology note Database, Methodologies and tools used for studying the impacts of environmental flow Mission report Mapping and geographical coordinates of selected (physical) thresholds | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs |  | Completed
|  | 1.2.3.2 Collect and process information for various environmental indicators |  | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
|  | 1.2.3.3 Select thresholds and carry out analysis for current and future climate scenarios |  | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
|  | 1.2.3.4 Identify 2 to 3 areas (Ramsar Bagré dam for example) with appropriate dataset on ecosystem services to test the methodology |  | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
|  | 1.2.3.5Draft report with the methodologies and tools used for studying the impacts of environmental flow |  | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
|  | 1.2.3.6 Drafting an integrated basin-wide wetland policy to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) and capacity building of relevant stakeholders. |  | WMO | IUCN, VBA, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
|  | 1.2.3.7 Support for developing bankable national projects for promoting sustainable aquatic/terrestrial transition zone (ATTZ) for the depended bio-diversity | ToR of workshop, presentation and communication supports, Workshop report, Mission report Number of roadmaps for implementing workshop guidelines in each of the 6 countries | VBA | IUCN, OMM, GWP-WA, ECOWAS/ WRCC, NMHs, NHSs
Outcome 1.3: Risk management strategies in short, medium and long-term to be integrated into development plans (economic, social, environmental aspects)
Output 1.3.1 | Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 1.3.1.1 Design and develop the guideline presenting the whole process of risk maps development and future impacts on VCERs assessment with examples of implementation on high vulnerable urbans and agricultural areas | TdR consultant Guidelines | WMO | VBA, GWP-WA, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  | compeleted
|  | 1.3.1.2 Develop supplementary means of communication to reach a wider population (infographics, leaflets for schools, etc.) | Communication supports Pedagogical materials elaborated | GWP-WA | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  | compeleted
Output 1.3.2 | Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 1.3.2.1 Organize trainings and workshops with stakeholders (representatives of communities, local policy-makers and decision makers) to disseminate the information on future climate and risk changes and to obtain additional qualitative input | Concept Note Workshop reports roadmaps for implementing workshop guidelines in each of the 6 countries | GWP-WA | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  | compeleted
|  | 1.3.2.2 a) Design capacity building courses for NMHSs improving their competencies to periodically perform scenarios and assessments | training curriculum and guidelines | WMO (as this is next step of risk map development) | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant |  | On-going | X
|  | 1.3.2.2b) provide review to the training curriculum prepared in the abovesub-ctivities through the National agencies incharge | training curriculum and guidelines | VBA |  |  | On-going | X
|  | 1.3.2.3 a) Design and develop action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders | ToR consultant, Mission report including the action plan for risk management | WMO (as this is next step of risk map development) | VBA, WMO, NMSs, NHSs, CIMA, Geographic institute, Other relevant | WMO through CIMA is working with VBA, gwp-wa and countries stakeholders to develop the flood and drought risk management strategies for the Volta Basin. Once the final version of the strategy is available, it will be validated and approved by the VBA council of Ministers. | To be completed by May-June 2023 | X
|  | 1.3.2.3 a) review the action plan for risk management at medium and long term with the output from workshops and consultations with the stakeholders |  | VBA | Six national workshop organized |  | completed
Component 2: Develop concrete adaptation and environmentally friendly actions with an integrated approach
Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities
Output 2.1.1 | Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 2.1.1.1 Select the participants (hydrologists, meteorologists, IT and GIS experts, etc.) within the NMHSs and flood or drought related services (Defence, Agriculture, etc.) | Concept Note, Methodology Note, List of participants, Manual of training (curriculum), ToR of workshop, communication and presentation supports, Workshop Report | GWP-WA/WMO | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant |  | Completed
|  | 2.1.1.2 Develop the curriculum on the basis of the capacity building documentation developed by GWP and WMO for their programmes on flood and drought management taking into account hydro-meteorological and socio-economic conditions of target areas |  | WMO | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant |  | On-going-E-learning courses - final course to start from end of February 2023 | X
|  | 2.1.1.3 Organize the face-to-face training sessions at the transboundary level (with participants from each riparian country) including theoretical trainings and practical exercises |  | GWP-WA | WMO, VBA, NMSs, NHSs, CIMA, UNITAR, CAP-NET, Other relevant | GWP-WA is organizing the final distance learning course from mid-March 2023 until end of April 2023 on early warning dissemination, decision support system and response to warnings of floods and drought. Once completed a face-to-face regional training workshop will be oganized for conducting practical exercises and sharing experiences for improving the early warning services in the Volta Basin | Regional workshop organized and report is pending and to be completed by June 2023 | X
Output 2.1.2 | The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | Concept Note, mission report, List and characteristics of equipments | WMO | VBA, GWP-WA, Other relevant |  | Completed
|  | 2.1.2.2 Buy, install and test the equipment needed to create VoltAlarm EWS | Calls of tender, Equipments | WMO | WMO, GWP-WA, Other relevant
|  | 2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Webbased EWS | Concept note, Workshop report, presentation and communication supports | WMO | VBA, GWP-WA, Other relevant |  | Completed. Regional workshop organized in July 2022 | X | X | X
|  | 2.1.2.4 Write the operational manual including procedures and responsibilities | Manual including procedures and responsibilities | WMO | VBA, GWP-WA, Other relevant |  | On-going to be made available by Dec 2023 | X | X | X
|  | 2.1.2.5 Run and maintain the VoltAlarm system | Calls of tender, Equipments | WMO | WMO, NMHs, NHSs, CIMA, other relevant, DHI |  | On-going till end of project | X | X | X | X | X | X
Output 2.1.3 | The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | 2.1.3.1 Make an inventory of the gauging stations with real-time data transfer (or pseudo real-time) in the Volta Basin and prepare descriptive sheets for each station (location, equipment, data series, etc.) | Concept Note, Mission report | WMO | VBA and other relevant organization | WMO- conduct study at the national level with CIMA and NMHSs and water resoucres agencies VBA and GWP-WA to povide support in data collection at the national and regional levels If needed, a national or local level studies will be carried out. |  |  | X | X | X
|  | 2.1.3.2 Perform a field/desk study to check the availability and quality of the data and information related to runoff, rainfall and other relevant meteorological and agrometeorological data |  | WMO | VBA and other relevant organization | WMO- conduct study at the national level with CIMA and NMHSs and water resoucres agencies If needed, request National agencies to conduct field studies VBA and GWP-WA to provide support |  |  | X | X
|  | 2.1.3.3 Develop the database of hydro-meteorological parameters, or interconnect with existing platforms | Database updated | WMO | VBA and other relevant organization | WMO- Connect the national data and information collected from the new and existing stations to the MCH Database |  |  | X | X
|  | 2.1.3.4 Organize training for the NMHSs staff related to data collection, calibration and maintenance of equipment following WMO standards | Concept note, Workshop report, presentation and communication supports | WMO | VBA and other relevant organization | WMO- prepare ToR to install new hydrological stations and carry out training on the data collection, calibration and maintenance of stations VBA and GWP-WA to support countries in organizing training at the national or regional levels |  |  | X | X
Output 2.1.4 | Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | 2.1.4.1 Use topographic data, VCERs database, Floods and Drought risk maps to mark out the boundaries of the basin, sub-basins, highly vulnerable areas | Concept Note Database updated Mission reports | WMO | VBA and other relevant organization at the national and regional levels |  | On-going | X | X | X | X
|  | 2.1.4.2 Describe the thresholds for flood events and for drought period based on VCERs and risk maps for various risk levels (level 0: no risk, level 1: very low, level 2 : low, level 3: moderate, level 4: high) through consultations with technical services and local representatives |  | WMO | VBA and other relevant organization at the national and regional levels |  | On-going | X | X | X | X
|  | 2.1.4.3 Define the values of the thresholds for floods and for drought events for each zone or area close to a gauging station, in relationship with past events |  | WMO | VBA and other relevant organization at the national and regional levels |  |  | X | X | X | X
|  | 2.1.4.4 Link the environment threshold with the threshold of flood and drought |  | WMO | VBA and other relevant organization at the national and regional levels |  |  | X | X | X | X
Output 2.1.5 | The procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | 2.1.5.1 For the areas with available forecast models in the sub-basins (e.g. White Volta, Oti), create the procedure to use the outputs of the existing models within the network of centers producing VoltAlarm (NMHSs and VBA) | Concept Note software to collect the meteorological and hydrological forecasts Procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily Mission reports | WMO | VBA, NMHs, NHSs, other relevant |  |  | X | X | X | X
|  | 2.1.5.2 For the areas not covered with hydrological models, develop charts and graphs (with various standard icons and images) to define the flood and drought indicators using hydro-meteorological data from past events |  | WMO | VBA, NMHs, NHSs, other relevant |  |  | X | X | X | X
|  | 2.1.5.3 Write the software to collect the meteorological and hydrological forecasts and to calculate the daily warning levels for each of the sub-basin and vulnerable areas |  | WMO | VBA, NMHs, NHSs, other relevant |  |  | X | X | X | X
|  | 2.1.5.4 Design and develop the interface to gather all individual warning levels on the main system at the VBA observatory |  | WMO | VBA, NMHs, NHSs, other relevant |  |  | X | X | X | X
Output 2.1.6 | The web-based Early Warning dissemination interface for VoltAlarm is designed and developed | 2.1.6.1 Organize consultations with the end-users from national and regional agencies and from communities to gather their expectations related to their future use of the prototype proposed on Figure 10 (background maps, zooms, types of graphs, location of evacuation centre, hospital, emergency centre, first-aid, etc.) | Concept Note Presentation supports Workshop reports | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant |  | completed. Regional workshop organized in January 2023
|  | 2.1.6.2 Develop and test the web-based dissemination interface |  | WMO | WMO, GWP-WA, NMHs, NHSs, other relevant |  | To start and complete in June 2024
Output 2.1.7 | Knowledge and awareness about VoltAlarm are increased within the user groups | 2.1.7.1 Carry out trainings and capacity development workshops with the NMHS professionals, local/national agencies and users of the web-based EWS | Concept Note Presentation supports | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant |  | To be started in May 2023 | X | X | X | X | X
Outcome 2.2: Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons
Output 2.2.1 | Pilot testing for a number of areas over the basin (Figure 8) during the monsoon and dry seasons are performed | 2.2.1.1 Finalize the selection of the pilot tests areas with the concerned agencies and communities on the basis of the draft list | ToR of the activity Mission reports Lists of the pilot tests areas | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | WMO- to prepare the methodology and VBA to support countries in finalizing the pilot sites | Completed | X
|  | Activity 2.2.1.2 Organize meetings on each of the pilot areas to assign the roles and responsibilities of the different groups of stakeholders during the tests and present the coordination and collaboration mechanism enabling first responders to receive and use efficiently the early warning information | Country specific reports | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to prepare the intiial consultation report of each sites in the countries | First part completed Second part on pilot testing is still pending | X
|  | Activity 2.2.1.3 Identify the good practices, challenges and limitations of products and services during the Flood and Drought events at each of the pilot testing locations |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  | X
|  | Activity 2.2.1.4 Raise awareness about the pilot testing using multi-media channels |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  |  | X | X | X
|  | Activity 2.2.1.5 Develop an action plan to further improve products and services after the pilot testing |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  |  | X | X | X
Ouput 2.2.2 | Output 2.2.2 Feedback from the series of pilot testing is collected | Activity 2.2.2.1 Organize national consultative workshops (participants from local/national agencies involved in Floods and Drought management) to share the knowledge (new methodologies, concepts and tools for effective forecasting and dissemination of early warnings) from the pilots tests |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  | X | X | X | X
|  | Activity 2.2.2.2 Collect feedbacks from the workshop participants highlighting their views and perception of developed products and services |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  |  |  | X | X
|  | Activity 2.2.2.3 Draft the series of reports on the experiences from the pilot testing and provide a summary of recommendations |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  |  |  | X | X
|  | Activity 2.2.2.4 Develop communication materials to disseminate the results of the pilot testing and describe the added value of VoltAlarm |  | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant | Countries to rpepare the intiial consultation report of each sites in the countries |  |  | X | X | X | X | X
Output 2.2.3 | Development and implementation of community based flood and drought management |  | Concept Note Presentation supports workshop reports | VBA | WMO, GWP-WA, NMHs, NHSs, other relevant |  | Completed
Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions
Output 2.3.1 | Knowledge and capacity development using the Flood Green Guide (FGG) | 2.3.1.1 Development of Training Curriculum of the FGG/IUCN Standard | Training Curriculum of the FGG/IUCN standards | WMO | GWP-WA, VBA, WWF/ IUCN |  | completed
|  | 2.3.1.2 Organize dedicated short courses (at least one per country) on the FFG approaches and concepts for targeted beneficiaries to disseminate knowledge on natural and nature-based solutions for flood management 2.3.1.3: Collect feedbacks from the workshop participants on their views and perception of FGG tools | Concept Note Presentation supports Workshop reports Training Curriculum of the FGG adapted | WMO | National/Regional and other project partners involved in the environmental and ecosystem services in each of the Volta Basin countries |  | completed
|  |  |  | VBA | National/Regional and other project partners involved in the environmental and ecosystem services in each of the Volta Basin countries |  | Completed
Output 2.3.2 | Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | 2.3.2.1 Finalization of Training Manual for mainstreaming gender in the E2E-EWS-F and flood management after review from expertise groups (E2E-EWS-F and Gender) such as OPACHE, ICIMOD etc. | Training Manual for mainstreaming gender in the E2E-EWS-F and flood management reviewed | WMO | GWP-WA, VBA, ECOWAS/EGDC, OTHER RELEVANT, CAP-NET, |  | On-going GWP-WA to send the action plan and recommendation for gender mainstreaming in E2E-EWS-FF and IFM
|  | 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | Concept Note Presentation supports Workshop reports Training Manual for mainstreaming gender in the E2E-EWS-F and flood management adapted | GWP-WA Before June 2021- Organize two workshops (cost for first two National workshops) | NMHSs,civil protection, communities (women groups or asosciation, youths, elderly, etc)
2.3.2.3Collect feedbacks from the workshop participants on c on mainstreaming gender in E2EEWS-F and IFM with other stakeholders
|  | 2.3.2.4 Recommend actions that would improve the participation of women and vulnerable groups into flood management and early warning | [5 empty] | X
Component 3: Strengthening policy and institutional capacity for integrated flood and drought management at the local, national and transboundary levels
Outcome 3.1 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin.
3.1.1 | The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 3.1.1.1 Conduct a desk study, and hold meetings with partners, to identify the status of climate and future socio-economic changes in the transboundary governance plans, policies and guidelines for flood and drought management | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  | Completed with regional workshop in May 2022
|  | 3.1.1.2 Develop a short report underlining the strengths together with the identified gaps and additional needs related to climate and development impacts |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant
|  | 3.1.1.3 Propose long-term actions for strengthening resilience and capacities at transboundary level to be implemented by VBA and the other regional agencies |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant
3.1.2 | Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policy-makers responsible for floods and drought management as well as other related fields (health, agriculture etc.) | ToR of the study National consultation reports Study report including i) the gaps and needs in policies and plans, and the key long-term strategies for floods and drought management; ii) recommendation at national level and needs for interconnection with transboundary policies | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant |  |  | X | X
|  | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans, and to highlight the key long-term strategies for floods and drought management |  | GWP-WA/VBA | WMO, NMHs, NHSs, other relevant |  |  |  | X
|  | 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies |  |  | WMO, NMHs, NHSs, other relevant |  |  |  | X
|  | 3.1.2.4 Present the recommendations to the policy-makers and ministries | Presentation and communication support Workshop report to adopt the recommandation | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant | [7 empty] | X
3.1.2 | Awareness of policy -makers from the six countries on the key long -term strategies for floods and drought management and environment impact is strengthened | 3.1.2.1 Describe the network of the relevant policymakers responsible for floods and drought management as well as other related fields (health, agriculture, ecosystem, forestry, soil and land management) | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  | One part completed with regional workshop in May 2022 and possibly one more workshop could be organized for the validation of the risk management strategy |  | X
|  | 3.1.2.2 Organize and conduct national workshops to identify the gaps and needs in policies and plans with special attention on safeguard actions for minimizing direct and indirect risks arising from the project activities, and to highlight the key long-term trategies for floods and drought management |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X
|  | 3.1.2.3 Collect feedbacks and recommendation at national level and needs for interconnection with transboundary policies |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X
|  | 3.1.2.4 Present the recommendations to the policy-makers and ministries |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant
3.1.3 | Experiences of local communities on key long-term strategies for floods and drought management are collected | Activity 3.1.3.1 Draft a report with evidence-based experiences at local levelns, policies and guidelines for flood and drought management | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  | To be started |  | X
|  | Activity 3.1.3.2 Organize and conduct local workshops to get a wider input of communities on possible solutions and arrangements for improving socio-economic development. |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X
|  | Activity 3.1.3.3 Collect feedbacks and recommendation at local level and provide input on the needs for relationships to national policies |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X
Outcome 3.2 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin.
3.2.1 | Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to risk reduction and EWS | Activity 3.2.1.1 Organize and conduct workshops to disseminate the revised, or new, plans, policies and guidelines on climate adaptation measures in the Volta Basin. | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  | To be started |  | X | X | X | X
|  | Activity 3.2.1.2 Collect feedbacks, suggestions and recommendations from the workshop participants on the links between activities of National Programmes and the Volta basin project |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X | X | X | X
|  | Activity 3.2.1.3 Identify roles and responsibilities of the individual organizations and define the coordination mechanism to improve the implementation of the climate change adaptation measures |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X | X | X | X
3.2.2 | Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | Activity 3.2.2.1 Launch national consultations in the six countries to gather feedback on the effective coordination between national and transboundary policies in the framework of floods and drought management and climate adaptation | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  | To be started |  | X | X | X | X
|  | Activity 3.2.2.2 Draft a report with recommendations from the consultations |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X | X | X | X
|  | Activity 3.2.2.3 Organize the dissemination of the report to policy-makers |  | VBA | GWP-WA, WMO, NMHs, NHSs, other relevant |  |  |  | X | X | X | X
Outcome 3.3 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin.
3.3.1 | Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Activity 3.3.1.1 Conduct a desk study and consultation of local stakeholders to gather examples of best practices for flood and drought risk reduction and climate adaptation related measures | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at transboundary level | GWP-WA | WMO, VBA, NMHs, NHSs, other relevant |  |  |  |  | X | X | X
|  | Activity 3.3.1.2 Develop capacity building documentation for local communities with the help of the local stakeholders |  | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant |  |  |  |  | X | X | X
|  | Activity 3.3.1.3 Draft report on recommendations from local communities |  | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant |  |  |  |  | X | X | X
3.3.2 | Collaboration with local communities and organizations in finalizing policies and procedures to manage risks and to adapt to climate change | Activity 3.3.2.1 Prepare a framework of safeguard actions for community involvement on long term disaster risk reduction with local stakeholders | ToR of the study Workshop valdation report Study reports Long-term actions plan for strengthening resilience and capacities at local and national to increase local participation | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant stakeholders | [5 empty] | X | X
|  | Activity 3.3.2.2 Conduct community-based workshops with agencies, local communities and organizations to prioritize adaptation measures |  | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant stakeholders | [5 empty] | X | X | X
|  | Activity 3.3.2.3 Collect feedbacks, suggestions and recommendations |  | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant stakeholders | [5 empty] | X | X | X
|  | Activity 3.3.2.4 Propose action plans at local and national levels to increase local participation |  | GWP-WA | VBA, WMO, NMHs, NHSs, other relevant stakeholders | [5 empty] | X | X | X
Note on D76: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 32000+195000=227000
Note on E72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As the risk maps will be developed in the support of National partners, the action plan will provide necessary management and prevention plan to the Countries.

## Sheet1
3.1.1 | 0
3.1.2 | 70000
3.1.3 | 28000
3.2.1 | 0
3.2.2 | 30000
3.3.1 | 10000
3.3.2 | 10000